## README
Trailbuddies backlog
Prepared 21 Oct 2026 for Steve Gaita. Same story IDs as the Markdown doc and the GitHub issues.
Sheet | What it holds
Backlog | One row per user story. Edit Status, Sprint, Owner and GitHub # here; Points is calculated from Size.
Summary | Counts and points by milestone, priority, status and epic; all formulas, so it updates as you edit Backlog.
Personas | Who the stories are written for.
Screens | Wireframe screen IDs used in the Screens column.
Lists | Allowed values for Priority, Size (with points), Milestone and Status.
Cells you edit | Backlog: Status, Sprint, Owner, GitHub #, Notes (yellow headers). Everything else comes from the story source.
Size → points | XS=1, S=2, M=3, L=5, XL=8 (one point ≈ half a day of Claude-assisted work). Set in Lists.
Example row | MVP-ready stories look like ONB-02: Must · M · MVP · S2 · Status 'To do'.

## Backlog
ID | Epic | Epic name | Title | Persona / role | User story | Acceptance criteria (Given / When / Then) | Priority | Size | Points | Milestone | Sprint | Screens | Status | Owner | GitHub # | Notes
OFF-01 | OFF | Offline & sync | Installable PWA | Grace (parent) | As Grace (parent), I want to install the app to my tablet's home screen, so that it opens like a normal app. | 1. GIVEN I visit the site on Android Chrome WHEN I choose Install THEN it installs with the app icon and opens full-screen | Must | S | 2 | MVP | S0 | C01 | To do | Steve | 2
CNT-01 | CNT | Content & subjects | Content schema and validation | Steve (developer) | As Steve (developer), I want a JSON schema for items, units, lessons, trails, buddy scripts and badges, validated in CI, so that content can be added safely without code changes. | 1. GIVEN a unit JSON is missing a required field WHEN CI runs THEN validation fails with the file and field named 2. GIVEN an asset referenced in a unit is missing WHEN CI runs THEN validation fails | Must | M | 3 | MVP | S0 |  | To do | Steve | 1
SAF-01 | SAF | Privacy, safety & compliance | Minimal child data | Grace (parent) | As Grace (parent), I want only a nickname, birth month and year and avatar stored about my child, so that their privacy is protected. | 1. GIVEN a learner profile is created WHEN it's stored THEN no surname, email, photo of the child, location or free text is collected | Must | S | 2 | MVP | S0 | P04 | To do | Steve | 7
SAF-06 | SAF | Privacy, safety & compliance | No third-party trackers | Steve (developer) | As Steve (developer), I want a CI check that blocks third-party analytics and ad SDKs, so that children are never tracked. | 1. GIVEN a PR adds a dependency on a known analytics/ad SDK WHEN CI runs THEN the build fails with an explanation | Must | S | 2 | MVP | S0 |  | To do | Steve | 8
OPS-01 | OPS | Platform & DevOps | Monorepo and CI | Steve (developer) | As Steve (developer), I want a pnpm + Turborepo monorepo with lint, tests and content validation on every PR, so that broken code never reaches main. | 1. GIVEN I open a PR WHEN CI runs THEN lint, unit, component, API and content checks run and block merge on failure | Must | M | 3 | MVP | S0 |  | To do | Steve | 3
OPS-02 | OPS | Platform & DevOps | Preview deploys | Steve (developer) | As Steve (developer), I want a preview URL for every PR, so that I can check changes on the tablet before merging. | 1. GIVEN I open a PR touching apps/web WHEN the preview deploys THEN the PR shows a link and Playwright smoke tests run against it | Must | S | 2 | MVP | S0 |  | To do | Steve | 4
OPS-03 | OPS | Platform & DevOps | API deploy to the VPS | Steve (developer) | As Steve (developer), I want API images built and deployed to the VPS with Docker Compose, so that deploys are one step. | 1. GIVEN I merge to main WHEN CI runs THEN the image is pushed to GHCR and the staging stack pulls and restarts with a health check 2. GIVEN a tag is pushed WHEN the release job runs THEN the database is backed up, migrations run, and production updates | Must | M | 3 | MVP | S0 |  | To do | Steve | 5
OPS-04 | OPS | Platform & DevOps | Backups and restore drills | Steve (developer) | As Steve (developer), I want automated database backups to R2 and a monthly restore test, so that I can recover from failure. | 1. GIVEN it's 02:00 WHEN the backup job runs THEN a compressed dump is uploaded to R2 with 30-day retention 2. GIVEN the monthly drill runs WHEN a backup is restored to a scratch database THEN row counts match and the result is logged | Must | S | 2 | MVP | S0 |  | To do | Steve | 6
LOC-01 | LOC | Languages & localisation | Every string ready for translation | Steve (developer) | As Steve (developer), I want all UI text, buddy lines and content words stored by key in language files, so that adding a language later needs translation work only, not code changes. | 1. GIVEN a component contains a hard-coded user-facing string WHEN CI runs the i18n lint THEN the PR fails naming the file and line 2. GIVEN a key is missing in a non-English language WHEN the app renders it THEN the English text is shown and a warning is logged in development | Must | M | 3 | MVP | S0 |  | To do | Steve | 215
LES-01 | LES | Lessons & exercises | Lesson runner | Amani (Seedling) | As Amani (Seedling), I want a short lesson of 5–8 quick activities with a progress bar, so that I finish before I get bored. | 1. GIVEN I tap a lesson stone WHEN the lesson starts THEN a progress bar shows activities left, and each activity renders the exercise type from the lesson spec 2. GIVEN I tap the exit button WHEN I confirm with the buddy THEN I return to the trail and partial progress is saved for answered items | Must | M | 3 | MVP | S1 | C07 | To do | Steve | 14
LES-02 | LES | Lessons & exercises | Exercise: listen & tap | Amani (Seedling) | As Amani (Seedling), I want to hear a word and tap the matching picture, so that I learn without reading. | 1. GIVEN the exercise starts WHEN the prompt plays THEN 2–4 pictures show depending on band and the prompt can be replayed with a speaker button 2. GIVEN I tap the right picture WHEN it's checked THEN it's marked correct with sound and the buddy reacts | Must | S | 2 | MVP | S1 | C07 | To do | Steve | 15
LES-03 | LES | Lessons & exercises | Exercise: match pairs | Zawadi (Sprout) | As Zawadi (Sprout), I want to match pictures with words or sounds by dragging or tapping, so that I connect what I see and hear. | 1. GIVEN 3–5 pairs are shown WHEN I drag or tap-tap a picture to its partner THEN a correct pair locks together; a wrong pair springs back with a hint after 2 misses | Must | S | 2 | MVP | S1 | C08 | To do | Steve | 16
LES-04 | LES | Lessons & exercises | Exercise: count | Amani (Seedling) | As Amani (Seedling), I want to count objects and tap the number, so that I practise counting. | 1. GIVEN objects are shown WHEN I tap each object THEN it is highlighted and counted aloud; then I tap the matching numeral | Must | S | 2 | MVP | S1 | C07 | To do | Steve | 17
LES-05 | LES | Lessons & exercises | Exercise: name it | Leo (Explorer) | As Leo (Explorer), I want to see a picture and choose its name, so that I practise recognising words. | 1. GIVEN I'm a reader (Explorer) WHEN the exercise shows THEN options are written words; for non-readers the options are spoken on tap | Must | S | 2 | MVP | S1 | C07 | To do | Steve | 18
LES-16 | LES | Lessons & exercises | Lesson complete screen | Zawadi (Sprout) | As Zawadi (Sprout), I want a finish screen with my stars and treasures, so that I know how I did and feel rewarded. | 1. GIVEN I finish the last activity WHEN the end screen shows THEN 1–3 stars based on first-try accuracy, treasures earned, and buttons for 'Next lesson' and 'Back to trail' 2. GIVEN I earned a badge in the lesson WHEN the end screen finishes THEN the badge celebration plays next | Must | S | 2 | MVP | S1 | C12 | To do | Steve | 19
LES-17 | LES | Lessons & exercises | Everything is spoken for non-readers | Amani (Seedling) | As Amani (Seedling), I want every instruction to be spoken, so that I can use the app before I can read. | 1. GIVEN I'm Seedling or Sprout band WHEN any screen shows an instruction THEN it's spoken automatically and a speaker button replays it | Must | S | 2 | MVP | S1 | C07 | To do | Steve | 20
ADP-01 | ADP | Adaptive learning | Difficulty adjusts automatically | Leo (Explorer) | As Leo (Explorer), I want lessons to get harder when I'm doing well and easier when I'm struggling, so that I'm always challenged but not stuck. | 1. GIVEN I get 3 stars in two consecutive lessons in a subject WHEN the next lesson is generated THEN difficulty within my band increases (more options, fewer hints) 2. GIVEN I get 1 star in two consecutive lessons WHEN the next lesson is generated THEN difficulty decreases | Must | M | 3 | MVP | S1 |  | To do | Steve | 9
ADP-03 | ADP | Adaptive learning | Item mastery tracking | Steve (developer) | As Steve (developer), I want a mastery score per child per item, so that weak items can be reviewed and shown to parents. | 1. GIVEN an item is answered WHEN the event is processed THEN seen and first-try-correct counts update and mastery is recalculated in the shared domain package | Must | S | 2 | MVP | S1 |  | To do | Steve | 10
ADP-04 | ADP | Adaptive learning | Spaced review | Zawadi (Sprout) | As Zawadi (Sprout), I want things I found hard to come back later, so that I remember them. | 1. GIVEN an item's mastery is below threshold WHEN time passes THEN the item is scheduled for review at 1, 3, 7 and 14 days and included in a review lesson | Must | M | 3 | MVP | S1 | C05, C10 | To do | Steve | 11
RWD-01 | RWD | Rewards: stars, treasures & shop | Earn stars per lesson | Zawadi (Sprout) | As Zawadi (Sprout), I want to earn 1–3 stars for each lesson, so that I can see how well I did. | 1. GIVEN I finish a lesson WHEN my first-try accuracy is ≥90% THEN I get 3 stars 2. GIVEN accuracy is 60–89% WHEN I finish THEN I get 2 stars; below 60% I still get 1 star 3. GIVEN I replay and do better WHEN I finish THEN the stone keeps my best stars | Must | S | 2 | MVP | S1 | C12 | To do | Steve | 21
CNT-02 | CNT | Content & subjects | Content packs and versioning | Steve (developer) | As Steve (developer), I want content built into versioned packs per subject and uploaded to storage, so that new lessons can ship without an app release. | 1. GIVEN I run the content build for release 2027.03.1 WHEN it finishes THEN per-subject packs and a manifest are uploaded and clients fetch updated packs on next launch | Must | M | 3 | MVP | S1 |  | To do | Steve | 12
CNT-09 | CNT | Content & subjects | Content tooling for writers | Steve (developer) | As Steve (developer), I want a content CLI to validate units, build packs, generate asset prompt sheets and normalise audio, so that making content is fast and consistent. | 1. GIVEN I run 'content-cli assets:prompts animals/farm' WHEN it finishes THEN a prompt sheet listing every item's illustration brief in the style guide is produced 2. GIVEN I run 'content-cli audio:normalise' WHEN it finishes THEN all clips are trimmed and loudness-normalised | Must | M | 3 | MVP | S1 |  | To do | Steve | 13
ONB-01 | ONB | Onboarding & accounts | Choose parent or teacher path | Grace (parent) | As Grace (parent), I want to say whether I'm a parent or a teacher when I first open the app, so that I'm taken through the set-up that fits me. | 1. GIVEN I open Trailbuddies for the first time WHEN I see the welcome screen THEN I can choose "I'm a parent" or "I'm a teacher" and a short animated intro of the buddies plays 2. GIVEN I chose "I'm a parent" WHEN I continue THEN I'm taken to sign-up with parent wording throughout | Must | S | 2 | MVP | S2 | P01 | To do | Steve | 29
ONB-02 | ONB | Onboarding & accounts | Sign up with email magic link | Grace (parent) | As Grace (parent), I want to create an account with just my email and a one-time link, so that I don't have to invent and remember another password. | 1. GIVEN I enter a valid email on sign-up WHEN I tap "Send my link" THEN an email with a sign-in link valid for 15 minutes is sent and the screen tells me to check my inbox 2. GIVEN I open the link on the same or another device WHEN the link is valid THEN I'm signed in and continue onboarding where I left off 3. GIVEN the link has expired or was already used WHEN I open it THEN I see a friendly message and can request a new link | Must | M | 3 | MVP | S2 | P02, P07 | To do | Steve | 30
ONB-06 | ONB | Onboarding & accounts | Give verifiable parental consent | Grace (parent) | As Grace (parent), I want to read a plain-language summary of what's collected and give consent, so that I know exactly what happens to my children's data before they play. | 1. GIVEN I reach the consent step WHEN I view it THEN I see what is collected, why, how long it's kept and my rights, in plain language with a link to the full policy 2. GIVEN I tick consent and complete the verification step required in my region WHEN I continue THEN a consent record with policy version, timestamp and method is stored 3. GIVEN I haven't consented WHEN I try to add a learner THEN I can't continue until consent is given | Must | M | 3 | MVP | S2 | P03 | To do | Steve | 31
ONB-07 | ONB | Onboarding & accounts | Add one or more learners | Grace (parent) | As Grace (parent), I want to add each of my children with a first name or nickname, birth month and year and an avatar, so that each child gets their own trail and progress. | 1. GIVEN I'm on "Who's learning?" WHEN I add Amani (born Mar 2023) and Zawadi (born Jun 2020) THEN two profiles are created with age bands Seedling and Sprout set from their birth dates 2. GIVEN I enter a full name WHEN I save THEN I'm reminded that a nickname is enough and only the first name field is stored 3. GIVEN my plan's learner limit is reached WHEN I try to add another THEN I see the limit and an option to upgrade (behind the parent gate) | Must | M | 3 | MVP | S2 | P04 | To do | Steve | 32
ONB-11 | ONB | Onboarding & accounts | Hand over to the child | Grace (parent) | As Grace (parent), I want a clear hand-over moment at the end of set-up, so that my child can start straight away without me navigating menus. | 1. GIVEN I finish onboarding WHEN I tap "Hand to Amani" THEN the app switches to the child experience and opens Meet the buddies for Amani 2. GIVEN I have several children WHEN I tap "Hand over" THEN the Who's playing? picker opens | Must | XS | 1 | MVP | S2 | P06, C03 | To do | Steve | 33
ONB-14 | ONB | Onboarding & accounts | Sign out and session handling | Grace (parent) | As Grace (parent), I want sessions to stay signed in on my devices until I sign out, so that I'm not asked to sign in every day but stay in control. | 1. GIVEN I'm signed in WHEN I return within 60 days THEN I remain signed in using a refresh token 2. GIVEN I choose "Sign out of all devices" WHEN I confirm THEN all refresh tokens are revoked and other devices return to the welcome screen | Must | S | 2 | MVP | S2 | P18 | To do | Steve | 34
FAM-01 | FAM | Family & learner profiles | Who's playing? profile picker | Zawadi (Sprout) | As Zawadi (Sprout), I want to tap my own avatar to start, so that I play on my own trail, not my brother's. | 1. GIVEN the family has two or more learners WHEN the child app opens THEN each learner's avatar and name is shown as a large button and a small 'Grown-ups' button sits in the corner 2. GIVEN I tap my avatar WHEN my profile has no picture password THEN my world map opens | Must | S | 2 | MVP | S2 | C01 | To do | Steve | 22
FAM-07 | FAM | Family & learner profiles | Switch learner from inside the child app | Grace (parent) | As Grace (parent), I want to switch the active learner quickly, so that siblings can take turns on one tablet. | 1. GIVEN a child is on their map WHEN they tap the avatar in the corner THEN the Who's playing? picker opens without passing the parent gate | Must | XS | 1 | MVP | S2 | C04, C01 | To do | Steve | 23
MAP-01 | MAP | World map & learning trail | World map of subjects | Amani (Seedling) | As Amani (Seedling), I want a map where every subject is a place I can tap, so that I can choose what to learn by exploring. | 1. GIVEN I'm on my world map WHEN it loads THEN each available subject appears as an illustrated place with its name spoken when tapped once 2. GIVEN my parent picked interests WHEN the map loads THEN those subjects are placed nearest the start | Must | M | 3 | MVP | S2 | C04 | To do | Steve | 24
MAP-02 | MAP | World map & learning trail | Winding subject trail | Zawadi (Sprout) | As Zawadi (Sprout), I want a winding path of stepping stones for each subject, so that I can see where I am and what comes next. | 1. GIVEN I tap Animals on the map WHEN the trail opens THEN units appear as stage banners and lessons as numbered stones along one continuous path, scrolled to my next lesson 2. GIVEN a lesson is completed WHEN I return to the trail THEN its stone shows 1–3 stars and the next stone glows | Must | L | 5 | MVP | S2 | C05 | To do | Steve | 25
MAP-09 | MAP | World map & learning trail | Friendly first visit | Amani (Seedling) | As Amani (Seedling), I want my first visit to the map to show me exactly where to start, so that I'm not confused by lots of places. | 1. GIVEN I have no progress yet WHEN my map opens THEN only the first subject place is highlighted, the buddy points to it and says 'Let's start here!', and other places are visible but quieter | Should | S | 2 | MVP | S2 | C29 | To do | Steve | 216
PAR-06 | PAR | Parent dashboard & controls | Parent gate | Grace (parent) | As Grace (parent), I want the grown-up zone behind a gate a young child can't pass, so that my child can't change settings or buy things. | 1. GIVEN a child taps 'Grown-ups' WHEN the gate shows THEN a sum such as 'What is 7 × 3?' with number buttons, or 'Hold for 3 seconds' as the accessible option, must be completed 2. GIVEN any learner on the account is 8 or older WHEN I open settings THEN I'm prompted to set a 4-digit PIN that replaces the sum | Must | S | 2 | MVP | S2 | C24 | To do | Steve | 35
OFF-03 | OFF | Offline & sync | Offline play with outbox | Zawadi (Sprout) | As Zawadi (Sprout), I want to play and earn rewards with no internet, so that nothing is lost. | 1. GIVEN the device is offline WHEN I complete lessons and buy an outfit THEN events are written to the local outbox and my map updates immediately 2. GIVEN the device reconnects WHEN sync runs THEN outbox events are sent in batches and acknowledged; none are duplicated | Must | L | 5 | MVP | S2 | C29 | To do | Steve | 26
OFF-04 | OFF | Offline & sync | Sync across devices | Grace (parent) | As Grace (parent), I want progress on any device to appear on all others, so that my children can switch devices. | 1. GIVEN Zawadi plays on the tablet WHEN I open my phone THEN her new stars and badges show after sync (within a minute when online) | Must | M | 3 | MVP | S2 | P08 | To do | Steve | 27
OFF-05 | OFF | Offline & sync | Conflict handling for edits | Steve (developer) | As Steve (developer), I want grown-up edits to merge with last-write-wins using server timestamps, so that edits from two devices don't corrupt data. | 1. GIVEN a lesson is edited offline on two devices WHEN both sync THEN the later edit wins and the earlier is kept in history for 30 days | Must | S | 2 | MVP | S2 |  | To do | Steve | 28
BUD-01 | BUD | Buddy tutor | Choose a buddy | Amani (Seedling) | As Amani (Seedling), I want to meet the buddies and pick the one I like, so that I have a friend who helps me learn. | 1. GIVEN I'm a new learner WHEN Meet the buddies opens THEN each buddy waves and introduces itself in its own voice when tapped 2. GIVEN I tap "Pick me!" on Zip WHEN I confirm THEN Zip becomes my buddy and appears on my map 3. GIVEN only one buddy is available (MVP) WHEN I view the screen THEN other buddies show as 'coming soon' and can't be selected | Must | S | 2 | MVP | S3 | C03 | To do | Steve | 36
BUD-03 | BUD | Buddy tutor | Buddy greets me by name | Amani (Seedling) | As Amani (Seedling), I want my buddy to say hello using my name, so that it feels like my own friend. | 1. GIVEN I open my map WHEN it's my first visit today THEN the buddy greets me by name (parent recording if one exists, otherwise the voice pack or device voice) and mentions what we did last time | Must | S | 2 | MVP | S3 | C04 | To do | Steve | 37
BUD-04 | BUD | Buddy tutor | Buddy introduces new concepts | Amani (Seedling) | As Amani (Seedling), I want my buddy to show and say each new thing before asking me, so that I'm never asked something I haven't seen. | 1. GIVEN a lesson contains an item I haven't seen WHEN the item first appears THEN the buddy shows the picture, says the word and one fun fact before any question about it | Must | S | 2 | MVP | S3 | C07 | To do | Steve | 38
BUD-05 | BUD | Buddy tutor | Hint ladder on wrong answers | Amani (Seedling) | As Amani (Seedling), I want gentle hints when I get something wrong, so that I never feel I've failed. | 1. GIVEN I tap a wrong answer WHEN it's my first miss on this question THEN there's no buzzer; the buddy repeats the question kindly 2. GIVEN it's my second miss WHEN the question resets THEN one wrong option disappears and the buddy points towards the right area 3. GIVEN it's my third miss WHEN the hint plays THEN the buddy shows and says the answer, I tap it to continue, and the item is scheduled for review | Must | M | 3 | MVP | S3 | C11 | To do | Steve | 39
BUD-06 | BUD | Buddy tutor | Varied celebrations | Leo (Explorer) | As Leo (Explorer), I want the buddy's praise to change and not slow me down, so that it stays fun and doesn't get annoying. | 1. GIVEN I answer correctly WHEN the buddy reacts THEN a reaction is chosen that wasn't used in my last answer, and I can tap to continue before it finishes 2. GIVEN I'm Explorer band or older WHEN I answer several in a row THEN celebrations are shorter | Must | S | 2 | MVP | S3 | C07, C12 | To do | Steve | 40
BUD-08 | BUD | Buddy tutor | Buddy script table | Steve (developer) | As Steve (developer), I want buddy lines to come from a script table keyed by event, buddy and language, so that writers can add lines without code changes. | 1. GIVEN a new line is added to the script table for event 'lesson_perfect' WHEN content is rebuilt THEN the line can be chosen at runtime without app code changes 2. GIVEN an event has no line for the chosen buddy WHEN it fires THEN a generic fallback line is used and a warning is logged in development | Must | S | 2 | MVP | S3 |  | To do | Steve | 41
MAP-03 | MAP | World map & learning trail | Locked and unlocked units | Zawadi (Sprout) | As Zawadi (Sprout), I want later units to unlock when I pass the checkpoint, so that I build up step by step. | 1. GIVEN I haven't passed the Farm animals checkpoint WHEN I tap a Wild animals stone THEN the buddy says it unlocks after the trophy and points to it 2. GIVEN I pass the checkpoint WHEN I return to the trail THEN the next unit's stones unlock with an animation | Must | S | 2 | MVP | S3 | C05, C14, C29 | To do | Steve | 48
LES-06 | LES | Lessons & exercises | Exercise: compare | Zawadi (Sprout) | As Zawadi (Sprout), I want to choose which group has more, fewer or the same, so that I understand comparing. | 1. GIVEN two groups are shown WHEN I tap the bigger group THEN it's checked and the buddy explains by counting both | Must | S | 2 | MVP | S3 | C07 | To do | Steve | 42
LES-07 | LES | Lessons & exercises | Exercise: sequence | Zawadi (Sprout) | As Zawadi (Sprout), I want to put 3–5 cards in order, so that I learn routines, life cycles and order. | 1. GIVEN cards are shuffled WHEN I drag them into slots THEN the order is checked when the last slot is filled and wrong cards wiggle | Must | S | 2 | MVP | S3 | C08 | To do | Steve | 43
LES-08 | LES | Lessons & exercises | Exercise: sort into bins | Zawadi (Sprout) | As Zawadi (Sprout), I want to drag items into 2–4 labelled baskets, so that I learn categories like land, water and air. | 1. GIVEN items and labelled bins are shown WHEN I drop an item in a bin THEN a correct drop stays; a wrong drop bounces back with the bin's label spoken | Must | M | 3 | MVP | S3 | C09 | To do | Steve | 44
LES-09 | LES | Lessons & exercises | Exercise: odd one out | Leo (Explorer) | As Leo (Explorer), I want to spot the item that doesn't belong, so that I think about categories. | 1. GIVEN 4 items are shown WHEN I tap the odd one THEN the buddy explains why it doesn't belong | Must | S | 2 | MVP | S3 | C07 | To do | Steve | 45
LES-10 | LES | Lessons & exercises | Exercise: case-match | Zawadi (Sprout) | As Zawadi (Sprout), I want to match capital and small letters, so that I learn both forms. | 1. GIVEN letter tiles are shown WHEN I match A to a THEN the pair locks and the letter sound plays | Must | S | 2 | MVP | S3 | C08 | To do | Steve | 46
LES-11 | LES | Lessons & exercises | Exercise: build a word | Zawadi (Sprout) | As Zawadi (Sprout), I want to drag letter tiles to spell a word, so that I practise spelling. | 1. GIVEN a picture and empty slots are shown WHEN I drag letters into slots THEN each letter's sound plays and the word is read when complete | Must | M | 3 | MVP | S3 | C07, C27 | To do | Steve | 47
BUD-07 | BUD | Buddy tutor | Effort-based encouragement | Zawadi (Sprout) | As Zawadi (Sprout), I want my buddy to notice when I kept trying, so that I feel proud even after a tricky lesson. | 1. GIVEN I finish a lesson with 3+ hints used WHEN the end screen shows THEN the buddy praises effort (e.g. 'You kept going!') rather than the score | Should | XS | 1 | MVP | S4 | C12 | To do | Steve | 52
BUD-09 | BUD | Buddy tutor | Buddy wears shop items | Zawadi (Sprout) | As Zawadi (Sprout), I want my buddy to wear the outfit I bought everywhere, so that my buddy feels like mine. | 1. GIVEN I equip a hat in the shop WHEN I return to the map or a lesson THEN the buddy is shown wearing the hat 2. GIVEN I play on another device WHEN it syncs THEN the same outfit is shown | Must | S | 2 | MVP | S4 | C18, C04 | To do | Steve | 53
MAP-07 | MAP | World map & learning trail | Review stones inserted automatically | Zawadi (Sprout) | As Zawadi (Sprout), I want review lessons to appear on my trail when I need practice, so that I don't forget things. | 1. GIVEN some items are due for review WHEN I open the trail THEN a review stone (different shape) appears before my next new lesson | Must | S | 2 | MVP | S4 | C05, C10 | To do | Steve | 58
GAM-01 | GAM | Games | Jigsaw puzzle from any picture | Amani (Seedling) | As Amani (Seedling), I want to do a jigsaw of a picture, so that I have fun and practise problem-solving. | 1. GIVEN a jigsaw opens WHEN my band is Seedling THEN the picture splits into 4 pieces with a faint outline to guide placement 2. GIVEN I'm Sprout or Explorer WHEN it opens THEN 9 or 16 pieces are used 3. GIVEN I place the last piece WHEN it snaps in THEN the full picture is shown, named aloud, and treasures are awarded | Must | M | 3 | MVP | S4 | C15 | To do | Steve | 54
GAM-03 | GAM | Games | Memory flip | Zawadi (Sprout) | As Zawadi (Sprout), I want to flip cards and find matching pairs, so that I practise memory with things I've learnt. | 1. GIVEN a memory game starts with items from a completed unit WHEN I flip two cards THEN a match stays face up with the word spoken; a non-match flips back after 1 second 2. GIVEN I'm Seedling WHEN the game starts THEN 6 cards are used; Sprout 8; Explorer 12 | Must | M | 3 | MVP | S4 | C16 | To do | Steve | 55
GAM-04 | GAM | Games | Games corner | Leo (Explorer) | As Leo (Explorer), I want a place to choose any unlocked game, so that I can play with what I've learnt. | 1. GIVEN I open Games corner WHEN it loads THEN unlocked games show with the topic they'll use; locked games show what unlocks them 2. GIVEN I start a game WHEN I choose a topic I've completed THEN the game uses that topic's items | Must | S | 2 | MVP | S4 | C17 | To do | Steve | 56
GAM-05 | GAM | Games | Games use any item set | Steve (developer) | As Steve (developer), I want every game to accept any item set (built-in or custom), so that new content works in games without code changes. | 1. GIVEN a custom lesson with 6 cards exists WHEN the memory game is launched with it THEN the game runs using those cards' images and audio | Must | S | 2 | MVP | S4 |  | To do | Steve | 57
RWD-02 | RWD | Rewards: stars, treasures & shop | Stars never decrease | Zawadi (Sprout) | As Zawadi (Sprout), I want stars to be a record of learning that's never spent, so that my progress never goes backwards. | 1. GIVEN I buy something in the shop WHEN the purchase completes THEN my star total is unchanged and only treasures are deducted | Must | XS | 1 | MVP | S4 | C18 | To do | Steve | 59
RWD-03 | RWD | Rewards: stars, treasures & shop | Earn treasures | Zawadi (Sprout) | As Zawadi (Sprout), I want to earn treasures for lessons, daily goals, perfect lessons, badges and games, so that I can save up for things. | 1. GIVEN I complete a lesson WHEN rewards are calculated THEN treasures are added according to the economy config and a count-up animation plays 2. GIVEN I've hit today's earning cap WHEN I complete another lesson THEN stars are still awarded but treasures are not, without telling me I'm capped | Must | M | 3 | MVP | S4 | C12 | To do | Steve | 60
RWD-04 | RWD | Rewards: stars, treasures & shop | Wallet from transactions | Steve (developer) | As Steve (developer), I want the treasure balance to be computed from an append-only transaction log, so that balances never desync across devices. | 1. GIVEN treasures were earned on two devices offline WHEN both sync THEN the balance equals the sum of all transactions 2. GIVEN a spend would take the server balance below zero after merge WHEN sync runs THEN the spend is reversed, the item returned to the shop and the child sees a gentle message | Must | M | 3 | MVP | S4 |  | To do | Steve | 61
RWD-05 | RWD | Rewards: stars, treasures & shop | Buddy shop | Zawadi (Sprout) | As Zawadi (Sprout), I want to spend treasures on outfits for my buddy, so that I can make my buddy look the way I like. | 1. GIVEN I open the shop WHEN it loads THEN items show price, a 'try on' preview and whether I can afford them 2. GIVEN I tap Buy on an item I can afford WHEN I confirm THEN treasures are deducted, the item goes to my wardrobe and the buddy wears it 3. GIVEN I can't afford it WHEN I tap it THEN the buddy says how many more treasures I need and offers to add it to my wishes | Must | M | 3 | MVP | S4 | C18 | To do | Steve | 62
RWD-08 | RWD | Rewards: stars, treasures & shop | Daily goal and gentle streak | Zawadi (Sprout) | As Zawadi (Sprout), I want a daily goal and a streak that doesn't punish me for missing a day, so that I want to come back without feeling bad. | 1. GIVEN my daily goal is 2 lessons WHEN I finish my second lesson THEN today fills in on the week strip and the buddy cheers 2. GIVEN I miss a day WHEN I return THEN up to 2 rest days a week are used automatically and nothing I've earned is lost | Must | S | 2 | MVP | S4 | C04, C12 | To do | Steve | 63
RWD-09 | RWD | Rewards: stars, treasures & shop | Economy config is tunable | Steve (developer) | As Steve (developer), I want earning amounts, caps and prices to live in one config, so that I can balance the economy without code changes. | 1. GIVEN I change the treasures per perfect lesson in the config WHEN content is released THEN new lessons award the new amount on all clients | Must | S | 2 | MVP | S4 |  | To do | Steve | 64
BDG-01 | BDG | Badges & achievements | Badge rule engine | Steve (developer) | As Steve (developer), I want badge rules evaluated on the device after every lesson and game, so that badges appear instantly, even offline. | 1. GIVEN a badge rule 'complete 10 three-star lessons' exists WHEN the 10th 3-star lesson completes offline THEN the badge is awarded immediately and an award event is queued for sync 2. GIVEN the same badge was already awarded on another device WHEN sync merges THEN the learner has the badge once | Must | M | 3 | MVP | S4 |  | To do | Steve | 49
BDG-02 | BDG | Badges & achievements | 15 built-in badges for the MVP | Zawadi (Sprout) | As Zawadi (Sprout), I want badges for learning milestones, mastery, effort, consistency and exploring, so that I have goals to aim for. | 1. GIVEN the MVP is released WHEN I open the badge book THEN 15 badges across those categories are listed, earned ones in colour and unearned ones as silhouettes with how to earn them spoken on tap | Must | M | 3 | MVP | S4 | C20 | To do | Steve | 50
BDG-03 | BDG | Badges & achievements | Badge celebration | Amani (Seedling) | As Amani (Seedling), I want a big celebration when I earn a badge, so that I feel proud. | 1. GIVEN I earn a badge WHEN the lesson or game ends THEN a full-screen celebration plays with the buddy's voice line, the badge flies into the badge book, and treasures count up | Must | S | 2 | MVP | S4 | C13 | To do | Steve | 51
MAP-06 | MAP | World map & learning trail | Family & Class Island | Zawadi (Sprout) | As Zawadi (Sprout), I want a special island on my map for lessons my family and teacher made, so that I can find them easily. | 1. GIVEN my parent assigned me a custom lesson WHEN I open my map THEN Family Island appears with a glowing marker for the new lesson 2. GIVEN my teacher assigned work WHEN I open my map THEN a 'From your teacher' signpost appears on Class Island with due work first | Must | M | 3 | MVP | S5 | C22, C04 | To do | Steve | 73
GAM-02 | GAM | Games | Jigsaw from a parent's photo | Grace (parent) | As Grace (parent), I want to turn one of my photos into a jigsaw, so that my child can puzzle over our own dog or grandparents. | 1. GIVEN I use the 'Picture puzzle' template with my photo WHEN my child opens it THEN the jigsaw uses my photo and after completion asks the question I set (e.g. 'Who is this?') | Must | S | 2 | MVP | S5 | C15, P12 | To do | Steve | 72
BLD-01 | BLD | Lesson Builder & custom trails | Create a card with photo, word and voice | Grace (parent) | As Grace (parent), I want to add a card with a photo (camera or upload), a label and my voice, so that I can teach my child about our world. | 1. GIVEN I open 'Add card' WHEN I take a photo THEN it's square-cropped, resized and EXIF-stripped on my device and shown immediately 2. GIVEN I hold the record button and say 'Daisy the cow' WHEN I release THEN a clip of up to 10 seconds is saved, trimmed and playable 3. GIVEN I don't record WHEN the card is used THEN the label is spoken by the voice pack or device voice | Must | M | 3 | MVP | S5 | P11 | To do | Steve | 65
BLD-02 | BLD | Lesson Builder & custom trails | Pick from the illustration library | Ms Priya (teacher) | As Ms Priya (teacher), I want to pick a picture from the built-in illustration library, so that I can make lessons without taking photos. | 1. GIVEN I tap 'Library' on a card WHEN I search 'giraffe' THEN matching illustrations show and the chosen one is attached | Must | S | 2 | MVP | S5 | P11 | To do | Steve | 66
BLD-04 | BLD | Lesson Builder & custom trails | Choose a lesson template | Grace (parent) | As Grace (parent), I want to choose a template like 'Learn the names', 'Sort them' or 'Picture puzzle', so that the app builds the activities for me. | 1. GIVEN I have 6 cards WHEN I choose 'Learn the names' THEN a lesson of explore → listen & tap → match → name it is generated 2. GIVEN a template needs something missing (e.g. Sort needs 2+ categories) WHEN I select it THEN I'm told what to add | Must | M | 3 | MVP | S5 | P12 | To do | Steve | 67
BLD-07 | BLD | Lesson Builder & custom trails | Preview as child | Grace (parent) | As Grace (parent), I want to play my lesson as my child would before assigning it, so that I can check it works. | 1. GIVEN I tap 'Preview as child' WHEN the preview runs THEN the lesson plays in the child UI with a 'Preview' banner and no progress or rewards are recorded | Must | S | 2 | MVP | S5 | P12 | To do | Steve | 68
BLD-08 | BLD | Lesson Builder & custom trails | Assign a custom lesson to my children | Grace (parent) | As Grace (parent), I want to choose which of my children get a lesson, so that each child gets what fits them. | 1. GIVEN I assign 'Our Pets' to Amani and Zawadi WHEN they open their maps THEN the lesson appears on Family Island for both | Must | S | 2 | MVP | S5 | P12, C22 | To do | Steve | 69
BLD-09 | BLD | Lesson Builder & custom trails | Edit and version custom lessons | Ms Priya (teacher) | As Ms Priya (teacher), I want to edit a lesson after it's been played, so that I can fix mistakes without breaking progress. | 1. GIVEN learners have progress on my lesson WHEN I add two cards THEN existing progress is kept (stable item IDs) and the new cards appear in the next session | Must | S | 2 | MVP | S5 | P10 | To do | Steve | 70
BLD-15 | BLD | Lesson Builder & custom trails | Offline-first media upload | Grace (parent) | As Grace (parent), I want my photos and recordings to work immediately and upload in the background, so that I never lose a card because the Wi-Fi dropped. | 1. GIVEN I'm offline WHEN I save a card with a photo THEN the card works on this device straight away and an upload is queued 2. GIVEN I reconnect WHEN the app is in the foreground or regains connectivity THEN queued uploads retry and the card switches to the cloud copy | Must | M | 3 | MVP | S5 | P11, P26 | To do | Steve | 71
BLD-16 | BLD | Lesson Builder & custom trails | See and retry failed uploads | Grace (parent) | As Grace (parent), I want to see which photos or recordings haven't uploaded yet and retry them, so that I know my cards are safe. | 1. GIVEN an upload has failed 3 times WHEN I open the Lesson Builder THEN a banner shows '2 items waiting to upload' with a Retry button, and the cards still work on this device 2. GIVEN storage on the device is full WHEN I try to add a photo THEN I'm told the device is full and offered to clear downloaded subjects I'm not using | Should | S | 2 | MVP | S5 | P26 | To do | Steve | 217
PAR-01 | PAR | Parent dashboard & controls | Parent home dashboard | Grace (parent) | As Grace (parent), I want a home screen with each child's activity this week, so that I can see at a glance how they're doing. | 1. GIVEN I open the grown-up zone WHEN it loads THEN each child shows minutes this week, lessons done, stars and their latest badge, with today's goal status | Must | M | 3 | MVP | S5 | P08 | To do | Steve | 74
PAR-02 | PAR | Parent dashboard & controls | Child progress detail | Grace (parent) | As Grace (parent), I want to see progress per subject, weak items and recent lessons for one child, so that I know where to help. | 1. GIVEN I open Zawadi's progress WHEN it loads THEN I see per-subject progress bars, a weekly activity chart, items she finds hard and her last 10 lessons 2. GIVEN I tap a weak item WHEN it expands THEN I see how often it was answered correctly and a suggestion like 'Practise together' | Must | M | 3 | MVP | S5 | P09 | To do | Steve | 75
PAR-03 | PAR | Parent dashboard & controls | Screen-time limit and bedtime lock | Grace (parent) | As Grace (parent), I want the app to stop at the daily limit and bedtime, so that screen time stays healthy. | 1. GIVEN Amani has used 20 of 20 minutes WHEN the limit is reached mid-lesson THEN the current activity finishes, then the buddy says goodbye and the break screen shows 2. GIVEN it's after bedtime WHEN Amani opens the app THEN the buddy is asleep and only the grown-ups button works | Must | M | 3 | MVP | S5 | C23, P18 | To do | Steve | 76
PAR-05 | PAR | Parent dashboard & controls | Family settings | Grace (parent) | As Grace (parent), I want to change daily goal, voice speed, sound and limits at any time, so that the app fits our routine. | 1. GIVEN I change voice speed to slow WHEN my child plays THEN all speech uses the slower rate | Must | S | 2 | MVP | S5 | P18 | To do | Steve | 77
SAF-02 | SAF | Privacy, safety & compliance | Strip photo metadata | Grace (parent) | As Grace (parent), I want location and camera data removed from my photos, so that my home location is never exposed. | 1. GIVEN I upload a photo with GPS EXIF WHEN it's processed on the device THEN all EXIF is removed before upload, and the server re-checks and rejects any file still carrying GPS data | Must | S | 2 | MVP | S5 | P11 | To do | Steve | 78
ONB-03 | ONB | Onboarding & accounts | Sign in with Google | Grace (parent) | As Grace (parent), I want to sign up or sign in with my Google account, so that set-up takes seconds on my Android phone. | 1. GIVEN I'm on sign-up WHEN I choose "Continue with Google" and approve THEN an account is created (or I'm signed in) using my Google email and I continue onboarding 2. GIVEN an account already exists with the same email via magic link WHEN I sign in with Google THEN both sign-in methods are linked to the one account | Must | S | 2 | MVP | S6 | P02 | To do | Steve | 89
ONB-05 | ONB | Onboarding & accounts | Country sets local rules and formats | Grace (parent) | As Grace (parent), I want to choose my country during sign-up, so that dates, my seasons unit, currency and the privacy rules match where I live. | 1. GIVEN I select my country WHEN I finish sign-up THEN the family's date format, 'My seasons' climate set and currency are set from the country, and the consent flow for that region is used 2. GIVEN I later change country in settings WHEN I save THEN formats update and I'm asked to re-confirm consent if the rules differ | Must | S | 2 | MVP | S6 | P02, P18 | To do | Steve | 90
ONB-09 | ONB | Onboarding & accounts | Choose interests and starting point | Grace (parent) | As Grace (parent), I want to tap my child's favourite things and what they can already do, so that the map shows the most exciting subjects first and they skip what they know. | 1. GIVEN I'm setting up Zawadi WHEN I tap Animals and Space as interests THEN those subjects appear first on her world map 2. GIVEN I tick "Knows her letters" WHEN I continue THEN Language starts at Letter sounds and earlier units show as completed with bronze stars 3. GIVEN I skip this step WHEN I continue THEN default subject order and the age-band start are used | Should | S | 2 | MVP | S6 | P05 | To do | Steve | 91
FAM-08 | FAM | Family & learner profiles | Family can use several devices | Grace (parent) | As Grace (parent), I want to sign in on my phone, the home tablet and a laptop, so that my children can play anywhere and progress follows them. | 1. GIVEN I sign in on a second device WHEN the device syncs THEN all learners, custom lessons and progress appear 2. GIVEN the plan allows a limited number of active devices WHEN I sign in on one more THEN I can sign out an old device from Settings | Must | S | 2 | MVP | S6 | P18 | To do | Steve | 87
ADP-02 | ADP | Adaptive learning | Parent can lock the level | Grace (parent) | As Grace (parent), I want to lock a child's difficulty in a subject, so that I can stop it moving if I know better. | 1. GIVEN I set Numbers to 'Locked: easier' for Amani WHEN lessons are generated THEN difficulty no longer adjusts in Numbers for Amani | Should | S | 2 | MVP | S6 | P09 | To do | Steve | 81
ADP-05 | ADP | Adaptive learning | Placement quiz | Leo (Explorer) | As Leo (Explorer), I want a quick quiz to skip what I already know, so that I don't waste time on easy lessons. | 1. GIVEN I open a subject for the first time WHEN I choose 'Show what you know' THEN a 2-minute adaptive quiz runs and units I pass are marked complete with bronze stars | Should | M | 3 | MVP | S6 | C05, C06 | To do | Steve | 82
BLD-03 | BLD | Lesson Builder & custom trails | Card extras: fact, category, number | Ms Priya (teacher) | As Ms Priya (teacher), I want to add a fun fact, a category tag and a number to a card, so that the buddy can say facts and the card works in sorting and counting games. | 1. GIVEN I tag cards 'land' and 'water' WHEN I choose the 'Sort them' template THEN the sort exercise uses those tags as bins | Should | S | 2 | MVP | S6 | P11 | To do | Steve | 83
BLD-06 | BLD | Lesson Builder & custom trails | Lesson settings | Grace (parent) | As Grace (parent), I want to set the age band, number of activities, hint level and unlocked games, so that the lesson suits my child. | 1. GIVEN I set band Seedling and 5 activities WHEN the lesson is generated THEN it uses 2–3 options per question and 5 activities | Should | S | 2 | MVP | S6 | P12 | To do | Steve | 84
PAR-04 | PAR | Parent dashboard & controls | Break reminders | Grace (parent) | As Grace (parent), I want the buddy to suggest a stretch break every N minutes, so that my child takes breaks. | 1. GIVEN break reminders are every 15 minutes WHEN 15 minutes pass THEN after the current lesson the buddy leads a 30-second stretch | Should | S | 2 | MVP | S6 | C23 | To do | Steve | 92
OFF-02 | OFF | Offline & sync | Download subjects for offline | Grace (parent) | As Grace (parent), I want subjects to be downloaded so they work without internet, so that we can learn on a trip or with no data. | 1. GIVEN I'm on Wi-Fi WHEN the app is opened THEN the content packs for my children's active subjects download in the background 2. GIVEN storage is low WHEN a download would exceed the quota THEN I'm told which subjects couldn't be downloaded and can free space | Must | M | 3 | MVP | S6 | P18, P26 | To do | Steve | 88
CNT-03 | CNT | Content & subjects | Asset review status | Steve (developer) | As Steve (developer), I want every asset to have a review status of draft, reviewed or approved, so that unapproved assets never reach production. | 1. GIVEN a production build includes an asset with status 'draft' WHEN CI runs THEN the build fails listing the asset | Must | S | 2 | MVP | S6 |  | To do | Steve | 85
CNT-04 | CNT | Content & subjects | MVP subjects: Numbers, Language, Animals, Colours, Shapes | Zawadi (Sprout) | As Zawadi (Sprout), I want the first units of five subjects, so that I have lots to learn in the beta. | 1. GIVEN the MVP is released WHEN I open my map THEN about 25 units across the five subjects at Seedling and Sprout are playable, each reviewed and approved | Must | XL | 8 | MVP | S6 | C04, C05 | To do | Steve | 86
ACC-02 | ACC | Accessibility | Reduced motion | Grace (parent) | As Grace (parent), I want a calm mode with fewer animations, so that my child doesn't get over-stimulated. | 1. GIVEN reduced motion is on (device or app setting) WHEN a celebration plays THEN it uses a short fade instead of confetti and bouncing | Must | S | 2 | MVP | S6 | P18 | To do | Steve | 79
ACC-03 | ACC | Accessibility | Captions for buddy speech | Grace (parent) | As Grace (parent), I want captions for everything the buddy says, so that children with hearing loss can follow. | 1. GIVEN captions are on WHEN the buddy speaks THEN a speech bubble shows the text in sync | Must | S | 2 | MVP | S6 | C07 | To do | Steve | 80
ONB-10 | ONB | Onboarding & accounts | Set family settings during onboarding | Grace (parent) | As Grace (parent), I want to set a daily goal, screen-time limit and bedtime lock during set-up, so that the app respects our routine from day one. | 1. GIVEN I'm on family settings WHEN I set a 20-minute limit and a 7:30 pm bedtime lock THEN these apply to every child profile and can be changed later in Settings | Must | S | 2 | MVP | S7 | P06 | To do | Steve | 99
FAM-03 | FAM | Family & learner profiles | Edit or remove a learner | Grace (parent) | As Grace (parent), I want to change a learner's nickname, avatar or birth date, or remove them, so that profiles stay accurate. | 1. GIVEN I edit Amani's birth date WHEN I save THEN his age band and look are recalculated; progress is kept 2. GIVEN I remove a learner WHEN I confirm twice THEN the profile and its progress are deleted after a 7-day undo window | Must | S | 2 | MVP | S7 | P08 | To do | Steve | 95
MAP-05 | MAP | World map & learning trail | Trail performance on budget tablets | Steve (developer) | As Steve (developer), I want the trail to scroll smoothly on a budget Android tablet, so that children don't experience lag. | 1. GIVEN a subject has 100+ stones WHEN the trail is scrolled on the reference tablet THEN scrolling holds ~60 fps and only stones near the viewport are mounted 2. GIVEN any stone is tapped WHEN it's measured THEN its touch target is at least 48 px | Must | M | 3 | MVP | S7 | C05 | To do | Steve | 97
LES-18 | LES | Lessons & exercises | Recorded audio overrides device voice | Grace (parent) | As Grace (parent), I want my own recordings to replace the device voice where I made them, so that my child hears a familiar voice. | 1. GIVEN I recorded the word 'Daisy' on a custom card WHEN the card is spoken THEN my recording plays instead of the voice pack or device voice | Must | S | 2 | MVP | S7 | P11 | To do | Steve | 96
OFF-06 | OFF | Offline & sync | App update without interrupting | Zawadi (Sprout) | As Zawadi (Sprout), I want updates not to interrupt my lesson, so that I can finish what I'm doing. | 1. GIVEN a new version is available WHEN I'm in a lesson THEN the update is applied the next time the app starts; grown-ups see a 'What's new' note | Must | S | 2 | MVP | S7 |  | To do | Steve | 98
OFF-07 | OFF | Offline & sync | Child-friendly offline and error states | Zawadi (Sprout) | As Zawadi (Sprout), I want a calm message from my buddy when something isn't available offline or goes wrong, so that I'm never shown a scary error. | 1. GIVEN a subject isn't downloaded and I'm offline WHEN I tap it THEN the buddy says 'This one needs the internet. Let's play something else!' and offers downloaded subjects 2. GIVEN an unexpected error happens in a lesson WHEN the app recovers THEN the buddy says 'Oops, let's try that again', my progress so far is kept, and the error is reported without child data | Must | S | 2 | MVP | S7 | C29 | To do | Steve | 218
SAF-03 | SAF | Privacy, safety & compliance | Export my family's data | Grace (parent) | As Grace (parent), I want to download all data held about my family, so that I can see what's stored. | 1. GIVEN I request an export WHEN it's ready (within 24 hours) THEN I get a download link to a ZIP with JSON and media, valid for 7 days | Must | M | 3 | MVP | S7 | P18 | To do | Steve | 102
SAF-04 | SAF | Privacy, safety & compliance | Delete my family's data | Grace (parent) | As Grace (parent), I want to delete my account and all my family's data, so that nothing is kept when we leave. | 1. GIVEN I request deletion and confirm with a sign-in link WHEN the 7-day undo window passes THEN all personal data and media are deleted from live systems, with backups expiring within 35 days | Must | M | 3 | MVP | S7 | P18, P26 | To do | Steve | 103
SAF-05 | SAF | Privacy, safety & compliance | Data retention jobs | Steve (developer) | As Steve (developer), I want automated retention rules (deleted lesson media after 30 days; inactive accounts after warnings), so that we meet our written retention policy. | 1. GIVEN a custom lesson was deleted 30 days ago WHEN the nightly job runs THEN its media objects are deleted from storage | Must | S | 2 | MVP | S7 |  | To do | Steve | 104
SAF-07 | SAF | Privacy, safety & compliance | Crash reports without child data | Steve (developer) | As Steve (developer), I want Sentry configured to scrub child data, so that debugging never exposes children. | 1. GIVEN an error occurs on a lesson screen WHEN Sentry captures it THEN learner names, media URLs and audio URLs are scrubbed before sending | Must | S | 2 | MVP | S7 |  | To do | Steve | 105
SAF-10 | SAF | Privacy, safety & compliance | Privacy policy and terms | Grace (parent) | As Grace (parent), I want a clear privacy policy and terms, so that I know my rights. | 1. GIVEN I open Privacy in settings WHEN it loads THEN I see a plain-language summary and the full policy, with version and date | Must | S | 2 | MVP | S7 | P18 | To do | Steve | 106
ACC-01 | ACC | Accessibility | Large touch targets | Amani (Seedling) | As Amani (Seedling), I want big buttons that are easy to tap, so that I don't tap the wrong thing. | 1. GIVEN any interactive element in the child app WHEN it's measured THEN it is at least 48 × 48 px with 8 px spacing | Must | S | 2 | MVP | S7 |  | To do | Steve | 93
ACC-07 | ACC | Accessibility | Contrast and colour independence | Steve (developer) | As Steve (developer), I want text contrast of at least 4.5:1 and no information by colour alone, so that everyone can see what matters. | 1. GIVEN axe checks run in CI WHEN a screen fails contrast THEN the PR is flagged; before launch it blocks | Must | S | 2 | MVP | S7 |  | To do | Steve | 94
OPS-05 | OPS | Platform & DevOps | Monitoring and alerts | Steve (developer) | As Steve (developer), I want uptime checks and error alerts, so that I hear about problems before parents do. | 1. GIVEN the API health check fails twice in a row WHEN the monitor runs THEN I get an alert by email and phone | Must | S | 2 | MVP | S7 |  | To do | Steve | 100
OPS-06 | OPS | Platform & DevOps | Feature flags | Steve (developer) | As Steve (developer), I want server-controlled feature flags, so that I can ship code dark and turn features on for beta families. | 1. GIVEN a flag is on for the beta cohort only WHEN a beta family opens the app THEN the feature shows only for them | Should | S | 2 | MVP | S7 |  | To do | Steve | 101
ONB-12 | ONB | Onboarding & accounts | First-steps card for parents | Grace (parent) | As Grace (parent), I want a short 'first steps' card after my child's first lesson, so that I discover custom lessons, badges and class linking without reading a manual. | 1. GIVEN my child has completed their first lesson WHEN I next open the grown-up zone THEN a dismissible card shows progress so far and links to make a lesson, make a badge and join a class | Could | S | 2 | P2 | S8 | P08 | To do | Steve | 111
FAM-02 | FAM | Family & learner profiles | Optional profile picture password | Zawadi (Sprout) | As Zawadi (Sprout), I want to protect my profile with three pictures, so that my little brother can't spend my treasures. | 1. GIVEN a parent enabled a picture password for me WHEN I tap my avatar THEN I'm asked to tap my 3 pictures in order 2. GIVEN I get it wrong 3 times WHEN I keep trying THEN a hint shows the first picture and the parent can reset it from the grown-up zone | Should | S | 2 | P2 | S8 | C02 | To do | Steve | 108
FAM-05 | FAM | Family & learner profiles | Invite a second parent | Tom (second parent) | As Tom (second parent), I want to be invited by email with equal access, so that I can follow and reward Leo from my own phone. | 1. GIVEN Grace invites tom@example.com as a parent WHEN Tom accepts the invite THEN Tom has full access to the family's learners, lessons and settings, and the invite is logged 2. GIVEN an invite isn't accepted in 7 days WHEN Tom opens it THEN it has expired and Grace can resend | Should | M | 3 | P2 | S8 | P19 | To do | Steve | 109
FAM-06 | FAM | Family & learner profiles | View-only carer role | Grace (parent) | As Grace (parent), I want to invite a grandparent or carer who can only see progress, so that family can cheer the kids on without changing settings. | 1. GIVEN I invite Grandma as 'View progress' WHEN she signs in THEN she sees progress and badges but can't edit learners, lessons, settings or purchases | Could | S | 2 | P2 | S8 | P19 | To do | Steve | 110
LES-19 | LES | Lessons & exercises | Record letter sounds once for every lesson | Grace (parent) | As Grace (parent), I want to record each letter and digraph sound once in a dedicated grown-ups screen, so that my child hears clean, correct phonics sounds everywhere instead of the device voice's approximations. | 1. GIVEN I open 'Letter sounds' in the grown-up zone WHEN the screen loads THEN every sound (a–z and digraphs such as sh, ch, th, ee) is listed with record, play and 'use device voice' controls and a count of how many are recorded 2. GIVEN I record /sh/ WHEN I play any lesson that uses /sh/ on any of the family's devices THEN my recording plays instead of the voice pack or device voice 3. GIVEN microphone permission is denied WHEN I tap record THEN I see how to enable it, and nothing else on the screen breaks | Should | M | 3 | P2 | S8 | P28 | To do | Steve | 221
BDG-06 | BDG | Badges & achievements | Weekly badge digest for parents | Grace (parent) | As Grace (parent), I want a weekly summary of badges my children earned, so that I can celebrate with them. | 1. GIVEN it's Sunday evening in my time zone WHEN the digest job runs THEN I receive an email listing each child's badges and time learnt this week, and can switch it off | Should | S | 2 | P2 | S8 | P18 | To do | Steve | 107
PAR-07 | PAR | Parent dashboard & controls | Notifications for parents | Grace (parent) | As Grace (parent), I want optional notifications for badges, wishes to approve and weekly summaries, so that I don't miss moments. | 1. GIVEN Zawadi asks for a wish WHEN I have notifications on THEN I get a push/email notification and can approve from it | Could | S | 2 | P2 | S8 | P16 | To do | Steve | 113
OPS-07 | OPS | Platform & DevOps | First-party product analytics | Steve (developer) | As Steve (developer), I want aggregated product metrics from our own event table, so that I can measure activation and retention without third-party trackers. | 1. GIVEN the weekly metrics job runs WHEN it finishes THEN a dashboard shows activation, weekly active learners, lessons per learner and retention, with no personal identifiers | Should | M | 3 | P2 | S8 |  | To do | Steve | 112
HLP-01 | HLP | Help & support | Help centre in the grown-up zone | Grace (parent) | As Grace (parent), I want short help articles inside the app, so that I can solve common problems without emailing anyone. | 1. GIVEN I open Help WHEN it loads THEN I see search plus topics (getting started, lessons, rewards, privacy, billing, offline) and the articles are available offline 2. GIVEN I'm on a screen with a help topic WHEN I tap the '?' icon THEN the matching article opens | Should | M | 3 | P2 | S8 | P30 | To do | Steve | 219
HLP-02 | HLP | Help & support | Contact support | Grace (parent) | As Grace (parent), I want to send a message to support from the app, so that I can get help with problems the articles don't solve. | 1. GIVEN I fill in the contact form WHEN I tick 'include device diagnostics' THEN app version, device model and recent error codes are attached, with no child names, media or progress data 2. GIVEN I submit WHEN the message is sent THEN I get an email confirmation with a reference number | Should | S | 2 | P2 | S8 | P30 | To do | Steve | 220
ONB-13 | ONB | Onboarding & accounts | Teacher sign-up | Ms Priya (teacher) | As Ms Priya (teacher), I want to sign up as a teacher with my school email, so that I can create classes without setting up a family. | 1. GIVEN I chose "I'm a teacher" WHEN I sign up and enter my school name THEN a teacher account is created and I land on Teacher home with a prompt to create my first class 2. GIVEN my school has a licence and my email domain matches WHEN I sign up THEN I'm offered to join the school's licence | Must | M | 3 | P2 | S9 | P01, T01, T00 | To do | Steve | 120
PAR-08 | PAR | Parent dashboard & controls | Linked teacher visibility | Grace (parent) | As Grace (parent), I want to see which teacher is linked and what they can see, so that I stay in control of my child's data. | 1. GIVEN Zawadi is linked to Ms Priya's class WHEN I open Family members THEN I see the class, the teacher and the scope, and can unlink at any time | Must | S | 2 | P2 | S9 | P19, P20 | To do | Steve | 121
CLS-01 | CLS | Classes & roster | Create a class | Ms Priya (teacher) | As Ms Priya (teacher), I want to create a class with a name, year group and age band, so that I can organise my learners. | 1. GIVEN I'm on Teacher home WHEN I create 'Class 1B, ages 5–6' THEN the class is created with a join code and QR and appears on my home | Must | S | 2 | P2 | S9 | T01 | To do | Steve | 114
CLS-02 | CLS | Classes & roster | Add students to the roster | Ms Priya (teacher) | As Ms Priya (teacher), I want to add students by first name or paste a list, so that set-up takes minutes. | 1. GIVEN I paste 26 first names WHEN I confirm THEN 26 roster entries are created with auto-assigned avatars and picture passwords 2. GIVEN two students share a name WHEN they're added THEN I'm prompted to add an initial to tell them apart | Must | M | 3 | P2 | S9 | T02 | To do | Steve | 115
CLS-03 | CLS | Classes & roster | Printable join cards | Ms Priya (teacher) | As Ms Priya (teacher), I want to print a card per student with the class code and QR for parents, so that parents can link their child at home. | 1. GIVEN I click 'Print parent letters' WHEN the PDF is generated THEN each page shows the child's name, the class code, a QR, and a plain-language note about what the teacher can see | Should | S | 2 | P2 | S9 | T02 | To do | Steve | 116
CLS-04 | CLS | Classes & roster | Parent links a child to a class | Grace (parent) | As Grace (parent), I want to enter the class code and choose which child it is, so that home and school share one learning record. | 1. GIVEN I enter Zawadi's class code WHEN I select Zawadi and confirm the roster entry 'Zawadi M.' THEN the profiles merge into one learner with combined history and the teacher sees the linked icon 2. GIVEN the code is wrong or expired WHEN I submit THEN I see a friendly error and can retry | Must | M | 3 | P2 | S9 | P20 | To do | Steve | 117
CLS-05 | CLS | Classes & roster | Scopes for teacher visibility | Grace (parent) | As Grace (parent), I want the teacher to see only class-assigned work and summary stats unless I allow more, so that my child's home learning stays private. | 1. GIVEN Zawadi is linked WHEN Ms Priya opens her progress THEN she sees assigned work and totals but not Family Island lessons 2. GIVEN I switch on 'Share all progress with teacher' WHEN she reopens it THEN she sees all subject progress | Must | M | 3 | P2 | S9 | P20, T04 | To do | Steve | 118
CLS-06 | CLS | Classes & roster | Class without parent accounts | Ms Priya (teacher) | As Ms Priya (teacher), I want to use the app with children whose parents haven't signed up, so that every child in my class can take part. | 1. GIVEN my school has accepted the school-consent terms WHEN I add a student with no parent account THEN the student can play in class; data is limited to what the school agreement allows | Must | M | 3 | P2 | S9 | T02 | To do | Steve | 119
HLP-03 | HLP | Help & support | Teacher getting-started guide | Ms Priya (teacher) | As Ms Priya (teacher), I want a short guide for setting up a class and the first week, so that I can get my class going without training. | 1. GIVEN I've just created my first class WHEN Teacher home loads THEN a 5-step checklist shows (add students, print parent letters, set up tablets, assign work, check progress) and ticks off as I do each | Could | S | 2 | P2 | S9 | T01, P30 | To do | Steve | 222
BLD-05 | BLD | Lesson Builder & custom trails | More templates | Ms Priya (teacher) | As Ms Priya (teacher), I want templates for 'Put in order', 'Count', 'Spelling list' and 'Quiz', so that I can make any kind of practice. | 1. GIVEN I choose 'Spelling list' and type 10 words WHEN I save THEN build-a-word and blend exercises are generated, using voice-pack audio for each word 2. GIVEN I choose 'Quiz' WHEN I write a question with 3 picture answers THEN the quiz lesson uses my questions in order | Should | L | 5 | P2 | S10 | P12 | To do | Steve | 126
BLD-13 | BLD | Lesson Builder & custom trails | Organise my library | Ms Priya (teacher) | As Ms Priya (teacher), I want to group my lessons into categories and reorder them, so that I can find things quickly. | 1. GIVEN I create a category 'Term 1' WHEN I drag lessons into it THEN the order and grouping save and sync | Should | M | 3 | P2 | S10 | P10 | To do | Steve | 127
BLD-14 | BLD | Lesson Builder & custom trails | Desktop Lesson Builder | Ms Priya (teacher) | As Ms Priya (teacher), I want the Lesson Builder to work well on a laptop with drag-and-drop file upload, so that I can build lessons quickly while planning. | 1. GIVEN I'm on a laptop WHEN I drag 10 image files onto the builder THEN 10 cards are created with labels from the file names, ready to edit | Should | M | 3 | P2 | S10 | T03 | To do | Steve | 128
CLS-07 | CLS | Classes & roster | Groups within a class | Ms Priya (teacher) | As Ms Priya (teacher), I want to create groups like 'Readers' and 'Starters', so that I can assign different work to each group. | 1. GIVEN I create a group and drag 8 students into it WHEN I assign work to the group THEN only those students receive it | Should | S | 2 | P2 | S10 | T02 | To do | Steve | 129
ASN-01 | ASN | Assignments & class insights | Assign work | Ms Priya (teacher) | As Ms Priya (teacher), I want to assign built-in units or my own lessons to a class, a group or individuals with an optional due date, so that everyone practises what we're learning in class. | 1. GIVEN I select Animals → Water animals and 'Group: Readers', due Friday WHEN I click Assign THEN the unit appears on those students' Class Island with a due badge 2. GIVEN a student completes it WHEN I view the assignment THEN their status changes to done with stars | Must | M | 3 | P2 | S10 | T03, C22 | To do | Steve | 122
ASN-02 | ASN | Assignments & class insights | Class progress heatmap | Ms Priya (teacher) | As Ms Priya (teacher), I want a grid of students × lessons coloured by stars, so that I can see who's stuck at a glance. | 1. GIVEN I open Class progress WHEN it loads THEN rows are students, columns are assigned lessons, cells show 0–3 stars and red marks for items struggled with 2. GIVEN I click a cell WHEN a panel opens THEN I see that student's answers and weak items for that lesson | Must | M | 3 | P2 | S10 | T04 | To do | Steve | 123
ASN-03 | ASN | Assignments & class insights | Struggling-items report | Ms Priya (teacher) | As Ms Priya (teacher), I want a list of the items the class finds hardest, so that I can reteach them. | 1. GIVEN an assignment has 10+ completions WHEN I open its insights THEN the 5 items with the lowest first-try accuracy are listed with the students struggling | Should | S | 2 | P2 | S10 | T04 | To do | Steve | 124
ASN-04 | ASN | Assignments & class insights | Export class progress | Ms Priya (teacher) | As Ms Priya (teacher), I want to export progress as CSV or PDF, so that I can include it in reports to parents and the school. | 1. GIVEN I click Export → CSV WHEN the file downloads THEN it contains student first names, assignments, stars and completion dates only | Should | S | 2 | P2 | S10 | T04 | To do | Steve | 125
CRM-01 | CRM | Classroom mode | Set a tablet to classroom mode | Ms Priya (teacher) | As Ms Priya (teacher), I want to set a shared tablet to my class, so that children can sign in themselves without email. | 1. GIVEN I sign in on a tablet and choose 'Use as classroom device for Class 1B' WHEN I confirm THEN the tablet opens to the class picker; the grown-up zone needs my PIN | Must | M | 3 | P2 | S10 | T06, C02 | To do | Steve | 130
CRM-02 | CRM | Classroom mode | Picture-password sign-in | Zawadi (Sprout) | As Zawadi (Sprout), I want to tap my class, my face picture and my 3 pictures to sign in, so that I can start quickly without reading or typing. | 1. GIVEN the tablet is in classroom mode WHEN I tap my avatar and my 3 pictures in order THEN my map opens 2. GIVEN I forget my pictures WHEN I tap 'Ask my teacher' THEN the teacher can show my pictures from their dashboard | Must | M | 3 | P2 | S10 | C02 | To do | Steve | 131
CRM-03 | CRM | Classroom mode | Auto sign-out on shared devices | Ms Priya (teacher) | As Ms Priya (teacher), I want children to be signed out after a lesson or inactivity, so that the next child doesn't play on someone else's profile. | 1. GIVEN a child finishes a lesson or is inactive for 3 minutes WHEN the timer fires THEN the tablet returns to the class picker | Must | S | 2 | P2 | S10 | C02 | To do | Steve | 132
CRM-05 | CRM | Classroom mode | Offline classroom | Ms Priya (teacher) | As Ms Priya (teacher), I want class tablets to work when the school Wi-Fi drops, so that the lesson isn't wasted. | 1. GIVEN assigned content was downloaded WHEN the Wi-Fi drops mid-lesson THEN children continue; results sync when the connection returns | Must | S | 2 | P2 | S10 | C02 | To do | Steve | 133
BDG-04 | BDG | Badges & achievements | Badge tiers | Leo (Explorer) | As Leo (Explorer), I want badges with bronze, silver and gold levels, so that I can keep improving. | 1. GIVEN I have bronze 'Perfect Ten' WHEN I reach 25 perfect lessons THEN the badge upgrades to silver with a smaller celebration | Should | S | 2 | P2 | S11 | C20, T05 | To do | Steve | 135
BDG-07 | BDG | Badges & achievements | Badges can't be taken away | Zawadi (Sprout) | As Zawadi (Sprout), I want badges I've earned to stay mine, so that I trust the rewards. | 1. GIVEN a grown-up deletes a custom badge rule WHEN I view my badge book THEN badges I already earned remain; a grown-up can hide a badge but not revoke it | Must | XS | 1 | P2 | S11 | C20 | To do | Steve | 136
BST-01 | BST | Badge Studio & Wish list | Design a custom badge | Grace (parent) | As Grace (parent), I want to design a badge with a shape, colour, icon or my own image, and a name, so that rewards match what matters in our family. | 1. GIVEN I open Badge Studio WHEN I pick a shape, colour and icon and name it 'Garden Helper' THEN a live preview shows the badge 2. GIVEN I upload an image WHEN it passes safety checks THEN it's cropped into the badge shape with EXIF stripped 3. GIVEN I record a message WHEN the badge is earned THEN my recorded message plays during the celebration | Must | M | 3 | P2 | S11 | P14 | To do | Steve | 137
BST-02 | BST | Badge Studio & Wish list | Set how a custom badge is earned | Ms Priya (teacher) | As Ms Priya (teacher), I want to choose a rule: complete content, reach a count, streak, mastery, assignment, manual award or a combination, so that badges reward exactly the behaviour I want. | 1. GIVEN I choose 'Complete content' and pick my 'Week 3 spelling' lesson WHEN I save THEN the badge is awarded automatically when a learner completes it 2. GIVEN I choose 'Combination' WHEN I add up to 3 conditions with AND/OR THEN the rule summary reads back in plain English before saving 3. GIVEN I choose 'Manual award' WHEN I save THEN the badge appears in my 'Award' list for chosen learners | Must | L | 5 | P2 | S11 | P15, T05 | To do | Steve | 138
BST-03 | BST | Badge Studio & Wish list | Attach treasures to a custom badge | Grace (parent) | As Grace (parent), I want to give treasures when a custom badge is earned, so that my child can spend the reward in the shop. | 1. GIVEN I set 50 treasures WHEN the value is within the cap THEN it's saved 2. GIVEN I enter more than the per-badge cap WHEN I try to save THEN I'm told the maximum and why (to keep the economy fair) | Must | S | 2 | P2 | S11 | P15 | To do | Steve | 139
BST-04 | BST | Badge Studio & Wish list | Real-world reward on a badge | Tom (second parent) | As Tom (second parent), I want to attach a real-world reward like 'Pick Friday's movie', so that the app connects to rewards at home. | 1. GIVEN I add a real-world reward to a badge WHEN Leo earns it THEN the reward appears on Leo's wishes as 'earned' and on my 'To deliver' list 2. GIVEN I mark it delivered WHEN Leo next opens his wishes THEN it shows as delivered with a thank-you animation | Must | M | 3 | P2 | S11 | P15, P16, C21 | To do | Steve | 140
BST-05 | BST | Badge Studio & Wish list | Manually award a badge remotely | Tom (second parent) | As Tom (second parent), I want to award a badge from my phone for something done at home, so that I can reward real-world effort while I'm away. | 1. GIVEN Leo tidied his room WHEN I tap Award on 'Tidy Champion' and choose Leo THEN Leo sees the celebration the next time he opens the app | Must | S | 2 | P2 | S11 | P16 | To do | Steve | 141
BST-06 | BST | Badge Studio & Wish list | Choose who can earn a badge | Ms Priya (teacher) | As Ms Priya (teacher), I want to make a badge available to one child, several children or a whole class, so that rewards fit the group. | 1. GIVEN I select 'Class 1B' WHEN I save the badge THEN every enrolled learner can earn it and new joiners get it automatically | Must | S | 2 | P2 | S11 | P15, T05 | To do | Steve | 142
BST-07 | BST | Badge Studio & Wish list | Wish list (save up for real rewards) | Zawadi (Sprout) | As Zawadi (Sprout), I want to save treasures towards a reward my parent set up, like 'a story of my choice', so that I have a big goal. | 1. GIVEN my parent created the wish '50 treasures = bedtime story of your choice' WHEN I open my wishes THEN it shows progress towards 50 treasures 2. GIVEN I have enough WHEN I tap 'Ask for it' THEN treasures are held and my parent gets an approval request 3. GIVEN my parent approves WHEN it's delivered THEN the treasures are spent; if declined they are returned | Should | M | 3 | P2 | S11 | C21, P16 | To do | Steve | 143
BST-08 | BST | Badge Studio & Wish list | Badge Studio safety checks | Steve (developer) | As Steve (developer), I want uploaded badge images checked like lesson uploads, so that nothing inappropriate appears to children. | 1. GIVEN a badge image is uploaded WHEN it's processed THEN EXIF is stripped, size limits apply and the automated content scan runs; flagged images are rejected with a reason | Must | S | 2 | P2 | S11 |  | To do | Steve | 144
SHR-01 | SHR | Sharing by code | Share a lesson by code | Ms Priya (teacher) | As Ms Priya (teacher), I want to create a 6-character code or QR for a lesson, trail or badge set, so that colleagues and parents can import it. | 1. GIVEN I tap Share on a lesson WHEN I confirm the safety checklist THEN a code and QR are created and I can copy or show them 2. GIVEN I revoke a code WHEN someone enters it THEN they're told it's no longer available; existing copies are unaffected | Must | M | 3 | P2 | S11 | P17 | To do | Steve | 146
SHR-02 | SHR | Sharing by code | Import by code | Grace (parent) | As Grace (parent), I want to enter a code and get my own copy, so that I can use lessons my child's teacher shared. | 1. GIVEN I enter a valid code WHEN I tap Import THEN a preview shows the lesson's cards and I can add a copy to my library 2. GIVEN the creator edits the original later WHEN I look at my copy THEN my copy is unchanged unless I re-import | Must | S | 2 | P2 | S11 | P17, P23 | To do | Steve | 147
SHR-03 | SHR | Sharing by code | Safety checklist before sharing | Steve (developer) | As Steve (developer), I want a checklist and automated face detection before a code is created, so that children's faces and personal details aren't shared. | 1. GIVEN a lesson contains an image with a detected face WHEN the creator tries to share THEN they must confirm the image isn't of a child or remove it 2. GIVEN the creator ticks 'No names or addresses' WHEN the code is created THEN the confirmation is logged with the share | Must | M | 3 | P2 | S11 | P17 | To do | Steve | 148
SHR-04 | SHR | Sharing by code | No child data travels in shares | Steve (developer) | As Steve (developer), I want shared content to contain only cards, media, templates and badges, so that no learner data ever leaves the family or class. | 1. GIVEN a lesson with learner progress is shared WHEN the share package is built THEN it contains no learner IDs, progress, names or recordings of children made via the app's progress features | Must | S | 2 | P2 | S11 |  | To do | Steve | 149
SHR-05 | SHR | Sharing by code | Report shared content | Grace (parent) | As Grace (parent), I want to report an imported lesson that seems inappropriate, so that unsafe content is removed. | 1. GIVEN I tap 'Report' on an imported lesson WHEN I choose a reason THEN the report goes to moderation and the code is suspended if it passes a threshold | Should | S | 2 | P2 | S11 | P17, M01 | To do | Steve | 150
ASN-05 | ASN | Assignments & class insights | Badge wall | Ms Priya (teacher) | As Ms Priya (teacher), I want a projectable wall of badges the class earned this week, so that we can celebrate together. | 1. GIVEN I open Badge wall in full screen WHEN it loads THEN each student's new badges this week are shown with first names only | Could | S | 2 | P2 | S11 | T06 | To do | Steve | 134
SAF-08 | SAF | Privacy, safety & compliance | Automated scan of shared uploads | Steve (developer) | As Steve (developer), I want uploaded images scanned for inappropriate content, so that nothing unsafe reaches children. | 1. GIVEN an uploaded image is flagged WHEN the scan completes THEN the image is hidden, the uploader is told why, and a review entry is created | Must | M | 3 | P2 | S11 | M01 | To do | Steve | 145
MOD-01 | MOD | Moderation | Moderation queue | Steve (developer) | As Steve (developer), I want one queue of reported shared content and automatically flagged uploads, so that unsafe content is reviewed quickly. | 1. GIVEN a parent reports an imported lesson or the scanner flags an image WHEN I open the moderation queue THEN the item shows with its reason, report count, share code, upload date and a preview, oldest first 2. GIVEN an item has been waiting more than 24 hours WHEN the queue loads THEN it's highlighted and I get a daily email reminder | Must | M | 3 | P2 | S11 | M01 | To do | Steve | 223
MOD-02 | MOD | Moderation | Moderation actions and audit log | Steve (developer) | As Steve (developer), I want to hide, restore, or suspend a share code, and to warn or suspend a creator account, so that I can act on reports consistently and show what was done. | 1. GIVEN I choose 'Hide image' on a flagged item WHEN I confirm with a reason THEN the image is replaced by a placeholder for everyone who has a copy, and the action is logged with who, when and why 2. GIVEN I suspend a share code WHEN someone tries to import it THEN they're told it's unavailable; existing copies stay but the flagged media is hidden | Must | M | 3 | P2 | S11 | M01 | To do | Steve | 224
MOD-03 | MOD | Moderation | Tell people the outcome | Grace (parent) | As Grace (parent), I want to hear back after I report something, and to be told if my own upload was hidden, so that I trust that reports are acted on and understand why something changed. | 1. GIVEN my report has been reviewed WHEN a decision is made THEN I get an email saying it was reviewed and the general outcome, without details about other users 2. GIVEN my image was hidden WHEN the action is taken THEN I get an email with the reason and how to appeal | Should | S | 2 | P2 | S11 | M01 | To do | Steve | 225
MOB-01 | MOB | Mobile app (React Native) | React Native CLI app scaffold in the monorepo | Steve (developer) | As Steve (developer), I want the bare React Native app in apps/mobile using shared packages, so that logic isn't duplicated. | 1. GIVEN the app is built WHEN it imports packages/domain, sync and content-schema THEN Metro resolves them and React isn't duplicated 2. GIVEN CI runs WHEN a release tag is pushed THEN a signed AAB is built with Gradle | Must | L | 5 | P3 | S12 |  | To do | Steve | 151
MOB-02 | MOB | Mobile app (React Native) | Native storage adapter | Steve (developer) | As Steve (developer), I want an op-sqlite storage adapter implementing the shared sync interface, so that the mobile app works offline like the web app. | 1. GIVEN the adapter passes the shared storage-adapter test suite WHEN the app runs offline THEN events queue and sync like on the web | Must | M | 3 | P3 | S12 |  | To do | Steve | 152
MOB-03 | MOB | Mobile app (React Native) | Child experience parity on Android | Zawadi (Sprout) | As Zawadi (Sprout), I want the Android app to have the same map, trail, lessons, games and rewards as the web app, so that I can use whichever device I have. | 1. GIVEN the Android app is installed WHEN I sign in THEN my profile, trail, wallet and badges match the web app after sync | Must | XL | 8 | P3 | S14 | C04, C05, C07 | To do | Steve | 153
MOB-04 | MOB | Mobile app (React Native) | Native camera and microphone in the Lesson Builder | Grace (parent) | As Grace (parent), I want the Android app to use the camera and microphone natively, so that making cards is fast on my phone. | 1. GIVEN I open Add card for the first time WHEN I tap Camera THEN the camera permission is requested at that moment (not at app launch) within the gated grown-up zone | Must | M | 3 | P3 | S16 | P11 | To do | Steve | 154
MOB-05 | MOB | Mobile app (React Native) | Play Store Families compliance | Steve (developer) | As Steve (developer), I want the Android app to meet Google Play's Families policy, so that it's approved and listed. | 1. GIVEN the app is submitted WHEN Play reviews it THEN data-safety, target-audience and Families declarations are accurate and no non-certified SDKs are included | Must | M | 3 | P3 | S17 |  | To do | Steve | 155
MOB-06 | MOB | Mobile app (React Native) | Maestro E2E on Android | Steve (developer) | As Steve (developer), I want the critical flows automated on an emulator, so that releases don't regress. | 1. GIVEN a release candidate is built WHEN Maestro runs THEN sign-up → lesson, offline → sync and builder flows pass | Must | M | 3 | P3 | S17 |  | To do | Steve | 156
MAP-04 | MAP | World map & learning trail | Cross-subject signposts | Leo (Explorer) | As Leo (Explorer), I want a signpost when a unit needs something from another subject, so that I know where to go first. | 1. GIVEN Time → Reading the clock needs Numbers → Counting by 5s WHEN I tap the locked unit THEN a signpost says 'Visit Numbers Mountain first!' and tapping it opens that unit | Should | S | 2 | P4 | S18 | C05 | To do | Steve | 160
LES-12 | LES | Lessons & exercises | Exercise: trace | Zawadi (Sprout) | As Zawadi (Sprout), I want to trace letters, numbers and shapes with my finger, so that I learn to write them. | 1. GIVEN a letter outline with start dot and arrow is shown WHEN I trace THEN strokes within tolerance in the right order complete the letter; off-path strokes show a gentle retry | Should | L | 5 | P4 | S18 | C07, C25 | To do | Steve | 157
LES-13 | LES | Lessons & exercises | Exercise: clock setter | Leo (Explorer) | As Leo (Explorer), I want to drag clock hands to show a time, so that I learn to read clocks. | 1. GIVEN a target time is said and shown WHEN I drag the hands THEN the minute hand snaps to 5-minute steps and the answer is checked when I tap Done | Should | M | 3 | P4 | S18 | C07, C26 | To do | Steve | 158
LES-14 | LES | Lessons & exercises | Exercise: true or false | Leo (Explorer) | As Leo (Explorer), I want to judge whether the buddy's claim is true, so that I think critically. | 1. GIVEN the buddy says 'A bat is a bird' WHEN I tap thumbs down THEN it's correct and the buddy gives the reason | Should | S | 2 | P4 | S18 | C07, C28 | To do | Steve | 159
GAM-06 | GAM | Games | Sorting race | Zawadi (Sprout) | As Zawadi (Sprout), I want items to fall and me to drag them into the right basket, so that sorting feels exciting. | 1. GIVEN the game starts WHEN items fall slowly THEN speed increases gently with correct sorts and never ends the game on mistakes | Should | M | 3 | P4 | S19 | C17 | To do | Steve | 161
GAM-07 | GAM | Games | Maze to the answer | Zawadi (Sprout) | As Zawadi (Sprout), I want to guide my buddy through a maze to the right answer, so that practice feels like play. | 1. GIVEN a maze with three answer exits shows WHEN I trace a path to an exit THEN the buddy walks it and reacts to the answer chosen | Could | M | 3 | P4 | S19 | C17 | To do | Steve | 162
GAM-08 | GAM | Games | Subject games pack | Leo (Explorer) | As Leo (Explorer), I want subject-specific games (planet line-up, what to wear, colour mixer, tangram, timeline ladder, feed the animal), so that each subject has a signature game. | 1. GIVEN I've completed the relevant unit WHEN I open Games corner THEN the subject's signature game is available | Should | XL | 8 | P4 | S19 | C17 | To do | Steve | 163
GAM-09 | GAM | Games | Quiz show | Leo (Explorer) | As Leo (Explorer), I want a 10-question quiz show hosted by my buddy across units I've finished, so that I can test myself. | 1. GIVEN I've completed 3+ units WHEN I start Quiz show THEN 10 mixed questions are drawn from my completed units and I get a final score with a personal best | Could | M | 3 | P4 | S19 | C17 | To do | Steve | 164
ADP-06 | ADP | Adaptive learning | Different band per subject | Leo (Explorer) | As Leo (Explorer), I want to be at a higher level in subjects I'm strong in, so that each subject fits me. | 1. GIVEN Leo placed into Voyager in Planets WHEN he opens Time THEN Time still starts at his age band | Should | S | 2 | P4 | S20 |  | To do | Steve | 165
ADP-07 | ADP | Adaptive learning | Legendary replay | Leo (Explorer) | As Leo (Explorer), I want to replay finished units at a harder setting, so that I can earn more and stay challenged. | 1. GIVEN I've completed a unit WHEN I tap its banner and choose 'Legendary' THEN the unit replays at the next band's settings and awards bonus treasures | Could | S | 2 | P4 | S20 | C05 | To do | Steve | 166
CNT-05 | CNT | Content & subjects | Launch subjects wave | Leo (Explorer) | As Leo (Explorer), I want Time, Weather & seasons, Plants, Opposites, Planets, Transport, Sports, Body, Positions, Directions & compass and Feelings, so that I can explore everything I'm curious about. | 1. GIVEN the launch release is out WHEN I open my map THEN 16 subjects with Seedling–Explorer units are available | Must | XL | 8 | P4 | S20 | C04 | To do | Steve | 167
CNT-06 | CNT | Content & subjects | My seasons localisation | Grace (parent) | As Grace (parent), I want the 'My seasons' unit to match our climate, so that my children learn the seasons they actually live through. | 1. GIVEN my country is Kenya WHEN my child reaches 'My seasons' THEN it teaches the long rains, short rains and dry seasons 2. GIVEN my country is the UK WHEN they reach it THEN it teaches spring, summer, autumn and winter | Should | M | 3 | P4 | S20 | C05 | To do | Steve | 168
ONB-08 | ONB | Onboarding & accounts | Add me too (adult learner) | Joseph (adult learner) | As Joseph (adult learner), I want the account owner to be able to add an adult learner profile, so that I can learn alongside the children without looking childish. | 1. GIVEN I'm on "Who's learning?" WHEN I choose "Add me too" or add an adult with birth year 18+ years ago THEN an adult profile is created with the adult look and the study-partner buddy tone | Should | S | 2 | P4 | S21 | P04, A01 | To do | Steve | 176
FAM-04 | FAM | Family & learner profiles | Automatic band move on birthday | Zawadi (Sprout) | As Zawadi (Sprout), I want to 'grow up' in the app around my birthday, so that it keeps feeling right for my age. | 1. GIVEN my birth month passes and I now fall in a new age stage WHEN I next open the app THEN my buddy celebrates my birthday, the look and starting band for new subjects update, and existing progress is kept | Should | S | 2 | P4 | S21 | C04 | To do | Steve | 175
BUD-02 | BUD | Buddy tutor | Change buddy later | Zawadi (Sprout) | As Zawadi (Sprout), I want to swap to a different buddy, so that I can try another friend. | 1. GIVEN I'm on my map WHEN I open my buddy's menu and choose 'Change buddy' THEN Meet the buddies opens; my outfits stay with each buddy and my progress is unchanged | Should | S | 2 | P4 | S21 | C03 | To do | Steve | 172
BUD-10 | BUD | Buddy tutor | Buddy grows up with the learner | Nia (Voyager) | As Nia (Voyager), I want my buddy to look and talk more grown-up as I get older, so that the app doesn't feel babyish. | 1. GIVEN my age stage is 8–12 WHEN I use the app THEN the buddy uses its 'coach' art set and tone 2. GIVEN I'm a teen or adult WHEN I open settings THEN I can switch the buddy to 'quiet' so it only appears when I ask | Should | M | 3 | P4 | S21 | A01 | To do | Steve | 173
BUD-11 | BUD | Buddy tutor | Three more buddies at launch | Zawadi (Sprout) | As Zawadi (Sprout), I want a choice of four buddies, so that I can pick the one that matches me. | 1. GIVEN the launch release is installed WHEN I open Meet the buddies THEN four buddies, each with its own voice, animations and script, are available | Must | L | 5 | P4 | S21 | C03 | To do | Steve | 174
RWD-06 | RWD | Rewards: stars, treasures & shop | Treasure room | Zawadi (Sprout) | As Zawadi (Sprout), I want to decorate my buddy's room with furniture, wallpaper and pets, so that I have a cosy place that's mine. | 1. GIVEN I own room items WHEN I open the treasure room THEN I can drag items to placement spots, and the layout saves and syncs | Should | L | 5 | P4 | S21 | C19 | To do | Steve | 177
RWD-07 | RWD | Rewards: stars, treasures & shop | Sticker albums with no randomness | Zawadi (Sprout) | As Zawadi (Sprout), I want to buy sticker packs that show exactly what's inside, so that I know what I'm getting. | 1. GIVEN I view a sticker pack WHEN I open its details THEN every sticker in the pack is shown before I buy; there are no random draws | Should | M | 3 | P4 | S21 | C19 | To do | Steve | 178
RWD-10 | RWD | Rewards: stars, treasures & shop | Game unlocks and trail decorations | Leo (Explorer) | As Leo (Explorer), I want to spend treasures on extra game themes and trail decorations, so that there's more to save up for. | 1. GIVEN I buy a 'space' theme for memory WHEN I start memory THEN I can pick the space card backs | Could | M | 3 | P4 | S21 | C18 | To do | Steve | 179
BDG-05 | BDG | Badges & achievements | Hidden surprise badges | Leo (Explorer) | As Leo (Explorer), I want secret badges I discover by accident, so that exploring is surprising. | 1. GIVEN a hidden badge exists WHEN I view the badge book THEN it shows as '???' until earned, then plays a special buddy dance | Could | S | 2 | P4 | S21 | C20 | To do | Steve | 169
BLD-11 | BLD | Lesson Builder & custom trails | Custom trails | Grace (parent) | As Grace (parent), I want to chain my lessons into a mini-trail with a checkpoint, so that I can make a learning journey like 'Our trip to the coast'. | 1. GIVEN I create a trail with 3 lessons and a jigsaw checkpoint WHEN my child opens Family Island THEN the trail appears as a winding path that unlocks in order | Should | L | 5 | P4 | S21 | C22, P13 | To do | Steve | 170
BLD-12 | BLD | Lesson Builder & custom trails | Remix a built-in unit | Ms Priya (teacher) | As Ms Priya (teacher), I want to copy a built-in unit and add or remove items, so that I can add local animals to Farm animals. | 1. GIVEN I tap 'Remix' on Farm animals WHEN I add 'camel' and remove 'pig' THEN a custom copy is saved in my library; the original is unchanged | Could | M | 3 | P4 | S21 | P10, P22 | To do | Steve | 171
BLD-10 | BLD | Lesson Builder & custom trails | Card and storage limits by plan | Grace (parent) | As Grace (parent), I want to see how many cards I've used, so that I'm not surprised by limits. | 1. GIVEN I'm on Free with 48 of 50 cards used WHEN I open the builder THEN a usage meter shows 48/50 and adding the 51st prompts an upgrade (behind the parent gate) | Should | S | 2 | P4 | S22 | P10 | To do | Steve | 180
PAY-01 | PAY | Plans & payments | View plans | Grace (parent) | As Grace (parent), I want to compare Free, Family and Classroom plans, so that I can decide whether to upgrade. | 1. GIVEN I open Plans behind the parent gate WHEN it loads THEN each plan's price, learner limit, content and creator limits are shown, with my current plan marked | Must | S | 2 | P4 | S22 | P21 | To do | Steve | 181
PAY-02 | PAY | Plans & payments | Subscribe on the web | Grace (parent) | As Grace (parent), I want to pay for the Family plan by card on the web, so that my children get everything. | 1. GIVEN I choose Family yearly WHEN I complete Stripe Checkout THEN the plan activates immediately on all devices and a receipt is emailed | Must | M | 3 | P4 | S22 | P21, P24 | To do | Steve | 182
PAY-03 | PAY | Plans & payments | Subscribe in the Android app | Grace (parent) | As Grace (parent), I want to subscribe through Google Play in the Android app, so that payment is simple on my phone. | 1. GIVEN I'm in the Android app WHEN I choose Family monthly THEN Google Play Billing is used, and the entitlement is verified server-side | Must | M | 3 | P4 | S22 | P21, P24 | To do | Steve | 183
PAY-04 | PAY | Plans & payments | Free tier limits | Grace (parent) | As Grace (parent), I want the Free plan to give real value with clear limits, so that I can try before paying. | 1. GIVEN I'm on Free WHEN my child opens a locked unit THEN the buddy says it's part of the full trail and nothing is shown to the child about prices; the parent sees upgrade info behind the gate | Must | M | 3 | P4 | S22 | C05, P21 | To do | Steve | 184
PAY-05 | PAY | Plans & payments | Classroom licence | Ms Priya (teacher) | As Ms Priya (teacher), I want to buy a Classroom licence for one teacher, so that my class gets full access. | 1. GIVEN I buy a Classroom licence WHEN it activates THEN all my students get full access at school and at home while enrolled | Must | M | 3 | P4 | S22 | T01, P24 | To do | Steve | 185
PAY-06 | PAY | Plans & payments | Manage and cancel subscription | Grace (parent) | As Grace (parent), I want to change or cancel my plan easily, so that I'm in control. | 1. GIVEN I tap Cancel WHEN I confirm THEN the plan stays active until the period ends, then reverts to Free without deleting content (excess custom cards become read-only) | Must | S | 2 | P4 | S22 | P21, P25 | To do | Steve | 186
PAY-07 | PAY | Plans & payments | No purchases from the child side | Steve (developer) | As Steve (developer), I want every purchase or price behind the parent gate, so that children can never be targeted with upsells. | 1. GIVEN any screen in the child app WHEN it's audited THEN no price, upgrade button or purchase link is reachable without passing the parent gate | Must | S | 2 | P4 | S22 |  | To do | Steve | 187
CLS-08 | CLS | Classes & roster | Move students between classes and archive | Ms Priya (teacher) | As Ms Priya (teacher), I want to move a student or archive a class at year end, so that my classes stay tidy. | 1. GIVEN the school year ends WHEN I archive Class 1B THEN students can still play at home with their families; class data is kept per retention policy then deleted | Could | S | 2 | P4 | S23 | T01 | To do | Steve | 191
CRM-04 | CRM | Classroom mode | Projector mode | Ms Priya (teacher) | As Ms Priya (teacher), I want to run a lesson on the projector for the whole class, so that I can teach a new topic together. | 1. GIVEN I start a unit in projector mode WHEN it runs THEN large visuals, buddy voice and a 'class answers' tap mode run without recording individual progress | Could | M | 3 | P4 | S23 | T06 | To do | Steve | 192
SAF-09 | SAF | Privacy, safety & compliance | Age-appropriate privacy by learner age | Nia (Voyager) | As Nia (Voyager), I want privacy rules to fit my age (under-13, 13–17, adult), so that my data is treated correctly. | 1. GIVEN a learner turns 13 WHEN the age rules are applied THEN the teen settings become available according to the family's country 2. GIVEN a learner is under 13 WHEN they use the app THEN no free-text input exists outside grown-up screens | Must | M | 3 | P4 | S23 | A01 | To do | Steve | 194
ACC-04 | ACC | Accessibility | Screen reader support in the grown-up zone | Grace (parent) | As Grace (parent), I want the grown-up zone to work with TalkBack and screen readers, so that blind or low-vision parents can manage the app. | 1. GIVEN TalkBack is on WHEN I navigate the parent home THEN every control has a label and the focus order is logical | Should | M | 3 | P4 | S23 | P08 | To do | Steve | 188
ACC-05 | ACC | Accessibility | Dyslexia-friendly font option | Leo (Explorer) | As Leo (Explorer), I want a dyslexia-friendly font for reading units, so that reading is easier for me. | 1. GIVEN the option is on WHEN a reading exercise shows THEN text uses the dyslexia-friendly font with increased spacing | Could | S | 2 | P4 | S23 | P18 | To do | Steve | 189
ACC-06 | ACC | Accessibility | Left-handed layouts | Zawadi (Sprout) | As Zawadi (Sprout), I want drag games to suit left-handed children, so that my hand doesn't cover the targets. | 1. GIVEN left-handed mode is on WHEN a sort exercise shows THEN bins appear on the left and items on the right | Could | S | 2 | P4 | S23 | C09 | To do | Steve | 190
OPS-08 | OPS | Platform & DevOps | Load and security review before launch | Steve (developer) | As Steve (developer), I want a load test and security review before public launch, so that launch day is calm. | 1. GIVEN the launch candidate is ready WHEN a load test of 1,000 concurrent syncs runs THEN p95 sync latency stays under 500 ms and no errors occur 2. GIVEN the security checklist runs WHEN it completes THEN auth, scopes, uploads and secrets handling are verified and findings fixed | Must | M | 3 | P4 | S23 |  | To do | Steve | 193
ONB-04 | ONB | Onboarding & accounts | Sign in with Apple | Grace (parent) | As Grace (parent), I want to sign in with Apple on an iPhone or iPad, so that I can use the app on Apple devices without a new password. | 1. GIVEN I'm on sign-up on iOS or Safari WHEN I choose "Continue with Apple" THEN an account is created, including when I hide my email | Should | S | 2 | P5 |  | P02 | To do | Steve | 210
MAP-08 | MAP | World map & learning trail | Regions for higher bands | Nia (Voyager) | As Nia (Voyager), I want each subject place to grow new regions as I level up, so that the trail keeps going. | 1. GIVEN I reach Voyager units in Numbers WHEN I open the map THEN Numbers Mountain shows a new 'summit' region with Voyager units | Could | M | 3 | P5 |  | C04 | To do | Steve | 203
LES-15 | LES | Lessons & exercises | Older-band exercise types | Nia (Voyager) | As Nia (Voyager), I want typed answers, labelling diagrams, read-and-answer and multi-step problems, so that lessons challenge me. | 1. GIVEN I'm in a Voyager unit WHEN an exercise asks for a typed number THEN a numeric keypad appears and answers are checked with forgiving matching 2. GIVEN a diagram exercise appears WHEN I drag labels onto the diagram THEN each label snaps to its target zone and is checked | Should | XL | 8 | P5 |  | A01 | To do | Steve | 202
ASN-06 | ASN | Assignments & class insights | Curriculum tags | Ms Priya (teacher) | As Ms Priya (teacher), I want units tagged with curriculum objectives, so that I can find units that match what I'm teaching. | 1. GIVEN I filter by 'Counting to 20' WHEN I browse units THEN units tagged with that objective are shown | Could | M | 3 | P5 |  | T03 | To do | Steve | 199
CNT-07 | CNT | Content & subjects | Higher-band units roll-out | Nia (Voyager) | As Nia (Voyager), I want Voyager units in Maths, Reading and Space first, so that the app grows with me. | 1. GIVEN Voyager content is released for a subject WHEN I'm 9–12 or placed at Voyager THEN the units appear on my trail | Should | XL | 8 | P5 |  | A01 | To do | Steve | 200
CNT-08 | CNT | Content & subjects | Post-launch subjects | Leo (Explorer) | As Leo (Explorer), I want Food, Family & community, Kindness & citizenship, Money & saving, Music, Countries & cultures, Coding & logic, so that there's always something new. | 1. GIVEN a post-launch subject wave is released WHEN I open my map THEN the new places appear with a 'New!' flag | Should | XL | 8 | P5 |  | C04 | To do | Steve | 201
OLD-01 | OLD | Older learners (teens & adults) | Mature look for older learners | Nia (Voyager) | As Nia (Voyager), I want a cleaner 'explorer' theme, so that the app feels like it's for me. | 1. GIVEN my age stage is 8–12 WHEN I open the app THEN the map and lessons use the explorer theme with optional dark mode | Should | L | 5 | P5 |  | A01 | To do | Steve | 205
OLD-02 | OLD | Older learners (teens & adults) | Teen sign-in | Nia (Voyager) | As Nia (Voyager), I want my own sign-in linked to my parent's account when I'm a teen, so that I can learn on my own device. | 1. GIVEN my parent enables teen sign-in for me (13+) WHEN I sign in with my own email or a family code THEN I get my profile only, and my parent keeps oversight | Should | M | 3 | P5 |  | A01, A02 | To do | Steve | 206
OLD-03 | OLD | Older learners (teens & adults) | Self-made flashcard trails | Joseph (adult learner) | As Joseph (adult learner), I want to make my own flashcard trail with self-rating, so that I can study anything. | 1. GIVEN I create a trail of 20 cards WHEN I study THEN cards are rated 'knew it / almost / not yet' and scheduled with spaced repetition | Should | L | 5 | P5 |  | A01 | To do | Steve | 207
OLD-04 | OLD | Older learners (teens & adults) | Personal records instead of confetti | Nia (Voyager) | As Nia (Voyager), I want to turn off celebrations and see personal records, so that I'm not distracted. | 1. GIVEN celebrations are off WHEN I finish a lesson THEN a compact summary shows stars, accuracy and personal bests | Should | S | 2 | P5 |  | A01 | To do | Steve | 208
OLD-05 | OLD | Older learners (teens & adults) | Family challenges | Joseph (adult learner) | As Joseph (adult learner), I want a cooperative family goal, so that we learn together. | 1. GIVEN Grace sets 'The family completes 30 lessons this week' WHEN any family learner completes a lesson THEN the shared progress bar fills; the reward goes to everyone when it's reached; there is no ranking between children | Could | M | 3 | P5 |  | A01, P08 | To do | Steve | 209
MOB-07 | MOB | Mobile app (React Native) | iOS app | Grace (parent) | As Grace (parent), I want an iPhone/iPad app, so that family members with Apple devices can use it. | 1. GIVEN the iOS build is released WHEN I install it from the App Store THEN it has the same features as Android, using Apple In-App Purchase for subscriptions | Should | XL | 8 | P5 |  |  | To do | Steve | 204
SCH-01 | SCH | School administration | School licence and seats | Sam (school admin) | As Sam (school admin), I want to buy a school licence and assign teacher seats, so that billing is one invoice. | 1. GIVEN I buy a 6-teacher licence WHEN I invite teachers by email THEN each accepted teacher gets Classroom features under the school | Should | L | 5 | P5 |  | S01 | To do | Steve | 211
SCH-02 | SCH | School administration | School-wide reports | Sam (school admin) | As Sam (school admin), I want usage and progress reports across all classes, so that I can see impact. | 1. GIVEN I open School reports WHEN it loads THEN I see active learners, lessons and progress per class, without individual child details unless the teacher shares them | Could | M | 3 | P5 |  | S02 | To do | Steve | 212
SCH-03 | SCH | School administration | Data processing agreement | Sam (school admin) | As Sam (school admin), I want to accept a data processing agreement online, so that the school meets its data-protection duties. | 1. GIVEN I open Legal in the school admin WHEN I accept the DPA THEN acceptance is recorded with name, role, date and version and a PDF copy is emailed | Should | S | 2 | P5 |  | S01 | To do | Steve | 213
SCH-04 | SCH | School administration | Shared school library | Sam (school admin) | As Sam (school admin), I want lessons shared across all teachers in the school, so that teachers don't duplicate work. | 1. GIVEN a teacher publishes a lesson to the school library WHEN another teacher opens the library THEN they can assign it directly | Could | M | 3 | P5 |  | S02 | To do | Steve | 214
AI-01 | AI | AI features | Say-it exercises with speech recognition | Zawadi (Sprout) | As Zawadi (Sprout), I want to say the answer out loud, so that I practise speaking and reading aloud. | 1. GIVEN a parent has enabled speech features WHEN a say-it exercise shows THEN my speech is recognised (on the device where possible), checked, and no audio is stored | Could | XL | 8 | P5 |  | C07 | To do | Steve | 195
AI-02 | AI | AI features | Guard-railed conversational hints | Leo (Explorer) | As Leo (Explorer), I want the buddy to explain things in different ways when I'm stuck, so that I understand, not just get the answer. | 1. GIVEN AI hints are enabled WHEN I'm stuck on a question THEN the buddy gives an age-appropriate explanation limited to the current exercise; there is no free chat | Could | XL | 8 | P5 |  | C11 | To do | Steve | 196
AI-03 | AI | AI features | AI-assisted lesson builder | Ms Priya (teacher) | As Ms Priya (teacher), I want to describe a lesson and get a draft to edit, so that I can build lessons in seconds. | 1. GIVEN I type 'A 6-card lesson about African birds for 5-year-olds' WHEN I generate THEN a draft lesson with cards from the licensed library and facts is created for me to review before anyone can play it | Could | L | 5 | P5 |  | P12 | To do | Steve | 197
AI-04 | AI | AI features | Auto-tag uploaded photos | Grace (parent) | As Grace (parent), I want photos to be auto-tagged with suggested labels and categories, so that making sort games is quicker. | 1. GIVEN I upload a photo of a goat WHEN processing finishes THEN 'goat' and 'farm animal' are suggested and I can accept or change them | Could | M | 3 | P5 |  | P11 | To do | Steve | 198
LOC-02 | LOC | Languages & localisation | Choose the app language per learner | Grace (parent) | As Grace (parent), I want to choose the language for each learner and for the grown-up zone, so that my children can learn in Kiswahili while I use English. | 1. GIVEN Kiswahili is available WHEN I set Amani's language to Kiswahili THEN his map, buddy voice, instructions and content words switch to Kiswahili; Zawadi stays in English 2. GIVEN a unit isn't translated yet WHEN Amani opens it THEN it's shown with a 'Coming soon in Kiswahili' tag and can be played in English if I allow it | Should | M | 3 | P5 |  | P29 | To do | Steve | 226
LOC-03 | LOC | Languages & localisation | Translated content and voice packs | Steve (developer) | As Steve (developer), I want content packs and voice packs built per language from the same unit files, so that each language ships without duplicating lesson logic. | 1. GIVEN a unit has Kiswahili translations and audio WHEN the content build runs THEN a Kiswahili pack is produced and validated, and missing items are listed in the build report | Should | L | 5 | P5 |  |  | To do | Steve | 227
LOC-04 | LOC | Languages & localisation | Bilingual mode | Grace (parent) | As Grace (parent), I want an option for the buddy to say each new word in two languages, so that my child learns English and Kiswahili side by side. | 1. GIVEN bilingual mode is on with English + Kiswahili WHEN a new item is introduced THEN the buddy says it in the learner's language first, then the second language, and the card shows both words | Could | M | 3 | P5 |  | P29 | To do | Steve | 228

## Summary
Backlog summary (all formulas: updates as the Backlog sheet changes)
Milestone | Title | Stories | Must | Should | Could | Points | Done (stories) | Done (points) | % points done
MVP | Phase 1 — MVP (closed web beta) | 110 | 100 | 10 | 0 | 264 | 0 | 0 | 0%
P2 | Phase 2 — Beta iteration + Classroom | 51 | 28 | 18 | 5 | 130 | 0 | 0 | 0%
P3 | Phase 3 — React Native Android app | 6 | 6 | 0 | 0 | 25 | 0 | 0 | 0%
P4 | Phase 4 — Breadth + public launch | 38 | 11 | 17 | 10 | 117 | 0 | 0 | 0%
P5 | Phase 5 — Post-launch | 23 | 0 | 13 | 10 | 106 | 0 | 0 | 0%
Total |  | 228 | 145 | 58 | 25 | 642 | 0 | 0 | 0%
MVP points per sprint (8 sprints) |  | 33
Epic | Name | Stories | Points | Done (points) | % done
ONB | Onboarding & accounts | 14 | 31 | 0 | 0%
FAM | Family & learner profiles | 8 | 16 | 0 | 0%
BUD | Buddy tutor | 11 | 26 | 0 | 0%
MAP | World map & learning trail | 9 | 25 | 0 | 0%
LES | Lessons & exercises | 19 | 52 | 0 | 0%
ADP | Adaptive learning | 7 | 17 | 0 | 0%
GAM | Games | 9 | 29 | 0 | 0%
RWD | Rewards: stars, treasures & shop | 10 | 27 | 0 | 0%
BDG | Badges & achievements | 7 | 15 | 0 | 0%
BST | Badge Studio & Wish list | 8 | 22 | 0 | 0%
BLD | Lesson Builder & custom trails | 16 | 44 | 0 | 0%
SHR | Sharing by code | 5 | 12 | 0 | 0%
PAR | Parent dashboard & controls | 8 | 19 | 0 | 0%
CLS | Classes & roster | 8 | 20 | 0 | 0%
ASN | Assignments & class insights | 6 | 15 | 0 | 0%
CRM | Classroom mode | 5 | 13 | 0 | 0%
OFF | Offline & sync | 7 | 19 | 0 | 0%
CNT | Content & subjects | 9 | 46 | 0 | 0%
PAY | Plans & payments | 7 | 18 | 0 | 0%
SAF | Privacy, safety & compliance | 10 | 24 | 0 | 0%
ACC | Accessibility | 7 | 15 | 0 | 0%
OLD | Older learners (teens & adults) | 5 | 18 | 0 | 0%
MOB | Mobile app (React Native) | 7 | 33 | 0 | 0%
OPS | Platform & DevOps | 8 | 20 | 0 | 0%
SCH | School administration | 4 | 13 | 0 | 0%
AI | AI features | 4 | 24 | 0 | 0%
LOC | Languages & localisation | 4 | 14 | 0 | 0%
MOD | Moderation | 3 | 8 | 0 | 0%
HLP | Help & support | 3 | 7 | 0 | 0%
Sprint |  | Stories | Points | Done (points)
S0 |  | 9 | 22 | 0
S1 |  | 13 | 31 | 0
S2 |  | 15 | 39 | 0
S3 |  | 13 | 29 | 0
S4 |  | 16 | 37 | 0
S5 |  | 15 | 37 | 0
S6 |  | 14 | 36 | 0
S7 |  | 15 | 33 | 0
S8 |  | 10 | 24 | 0
S9 |  | 9 | 23 | 0
S10 |  | 12 | 33 | 0
S11 |  | 20 | 50 | 0
S12 |  | 2 | 8 | 0
S13 |  | 0 | 0 | 0
S14 |  | 1 | 8 | 0
S15 |  | 0 | 0 | 0
S16 |  | 1 | 3 | 0
S17 |  | 2 | 6 | 0
S18 |  | 4 | 12 | 0
S19 |  | 4 | 17 | 0
S20 |  | 4 | 15 | 0
S21 |  | 11 | 35 | 0
S22 |  | 8 | 20 | 0
S23 |  | 7 | 18 | 0
S24 |  | 0 | 0 | 0

## Personas
Name | Age | Role | Summary | Needs | Frustrations
Amani | 3 | Learner (Seedling, 3–4) | Can't read yet. Loves animals and tapping things. Plays on the family's budget Android tablet, usually for 10–15 minutes after nursery, with Mum nearby. | Everything spoken aloud; big targets; no failure states; lots of praise; quick wins. | Small buttons, text instructions, anything that takes too long to load.
Zawadi | 6 | Learner (Sprout, 5–6) | Amani's older sister. Learning to read and count to 100. Very motivated by collecting stickers and dressing up her buddy. Plays at home and in class. | Visible progress; rewards to save up for; feeling 'big' compared with her little brother. | Repeating lessons she already knows; her brother playing on her profile.
Leo | 8 | Learner (Explorer, 7–8) | Confident reader, obsessed with space and football. Likes challenges and getting things right first time. | Harder questions, real facts, a sense of mastery; less babyish feedback. | Being made to do easy stuff; slow celebrations that stop him moving on.
Nia | 11 | Learner (Voyager, 9–12) | Uses the app for maths practice and planets. Has her own PIN. Wants it to feel grown-up. | A cooler look, typed answers, her own goals, privacy from younger siblings. | Cartoonish UI, being treated like a little kid.
Grace | 34 | Parent (account owner) | Mum of Amani and Zawadi. Works full-time, uses an Android phone. Wants screen time that is actually educational and wants to add the family's own world (their farm, their grandparents) to lessons. | Fast set-up; clear progress at a glance; making a custom lesson in under 5 minutes; control of screen time. | Ads, upsells aimed at kids, apps that need constant supervision.
Tom | 41 | Second parent / guardian | Leo's dad. Travels for work, checks progress from his phone and likes to award badges remotely for things Leo does at home. | View progress, award a badge, approve a wish from anywhere. | Being locked out because only one parent set up the account.
Ms Priya | 29 | Teacher (early-years / primary) | Teaches a class of 26 five-and-six-year-olds with 8 shared tablets and a projector. Makes her own weekly spelling and topic lessons. | Quick class set-up; assigning work to groups; seeing who's stuck; reusing and sharing lessons with colleagues. | Kids forgetting passwords; spending lesson time on logins; tools that don't work offline when the Wi-Fi drops.
Joseph | 46 | Adult learner | Grace's uncle. Is improving his reading and wants to learn alongside the grandchildren. Uses the 'Add me too' adult profile. | Adult look; no childish tone; private progress; start at the right level. | Feeling patronised; public comparisons.
Sam | 50 | School administrator | Runs a small primary school with 6 teachers. Buys the school licence and manages teacher seats. | Simple licence and seat management; data-protection paperwork; school-wide reports. | Per-teacher billing chaos; unclear data handling.
Steve | — | Developer / product owner | Builds the product solo with Claude. Needs fast feedback, safe releases and content that can be added without code changes. | Automated checks, reliable deploys, a content pipeline. | Manual, error-prone release steps.

## Screens
Screen | Title | Device | Prototype artboard | Stories (count)
P01 | Welcome | Phone | P01-Welcome.dc.html | 2
P02 | Sign up | Phone | P02-SignUp.dc.html | 4
P03 | Parental consent | Phone | P03-Consent.dc.html | 1
P04 | Add learners | Phone | P04-AddLearners.dc.html | 3
P05 | Interests & starting point | Phone | P05-Interests.dc.html | 1
P06 | Family settings & hand-over | Phone | P06-FamilySettings.dc.html | 2
P08 | Parent home | Phone | P08-ParentHome.dc.html | 6
P09 | Child progress | Phone | P09-ChildProgress.dc.html | 2
P10 | Lesson Builder: cards | Phone | P10-BuilderCards.dc.html | 4
P11 | Lesson Builder: add card | Phone | P11-BuilderAddCard.dc.html | 8
P12 | Lesson Builder: template & assign | Phone | P12-BuilderTemplate.dc.html | 7
P14 | Badge Studio: design | Phone | P14-BadgeDesign.dc.html | 1
P15 | Badge Studio: rule & reward | Phone | P15-BadgeRule.dc.html | 4
P16 | Wishes & awards | Phone | P16-Wishes.dc.html | 4
P17 | Share codes | Phone | P17-ShareCodes.dc.html | 4
P18 | Settings, limits & privacy | Phone | P18-Settings.dc.html | 12
P19 | Family members | Phone | P19-FamilyMembers.dc.html | 3
P20 | Join a class | Phone | P20-JoinClass.dc.html | 3
P21 | Plans | Phone | P21-Plans.dc.html | 5
C01 | Who's playing? | Tablet | Main.dc.html | 3
C02 | Classroom picture password | Tablet | C02-PicturePassword.dc.html | 5
C03 | Meet the buddies | Tablet | C03-ChooseBuddy.dc.html | 4
C04 | World map | Tablet | C04-WorldMap.dc.html | 12
C05 | Subject trail | Tablet | C05-Trail.dc.html | 12
C07 | Lesson: listen & tap | Tablet | C07-ListenTap.dc.html | 16
C08 | Lesson: match pairs | Tablet | C08-Match.dc.html | 3
C09 | Lesson: sort into bins | Tablet | C09-Sort.dc.html | 2
C11 | Lesson: hint | Tablet | C11-Hint.dc.html | 2
C12 | Lesson complete | Tablet | C12-LessonComplete.dc.html | 6
C13 | Badge earned | Tablet | C13-BadgeEarned.dc.html | 1
C14 | Unit checkpoint | Tablet | C14-Checkpoint.dc.html | 1
C15 | Game: jigsaw | Tablet | C15-Jigsaw.dc.html | 2
C16 | Game: memory | Tablet | C16-Memory.dc.html | 1
C17 | Games corner | Tablet | C17-GamesCorner.dc.html | 5
C18 | Buddy shop | Tablet | C18-Shop.dc.html | 4
C19 | Treasure room | Tablet | C19-TreasureRoom.dc.html | 2
C20 | Badge book | Tablet | C20-BadgeBook.dc.html | 4
C21 | My wishes | Tablet | C21-Wishes.dc.html | 2
C22 | Family & class island | Tablet | C22-Island.dc.html | 4
C23 | Time for a break | Tablet | C23-Break.dc.html | 2
C24 | Grown-ups gate | Tablet | C24-Gate.dc.html | 1
T01 | Teacher home | Desktop | T01-TeacherHome.dc.html | 5
T02 | Class roster & join code | Desktop | T02-Roster.dc.html | 4
T03 | Assign work | Desktop | T03-Assign.dc.html | 3
T04 | Class progress | Desktop | T04-ClassProgress.dc.html | 4
T06 | Classroom mode & badge wall | Desktop | T06-ClassroomMode.dc.html | 3
A01 | Teen / adult home | Tablet | A01-OlderHome.dc.html | 10
P07 | Check your email / expired link | Phone | P07-CheckEmail.dc.html | 1
P13 | Custom trail builder | Phone | P13-TrailBuilder.dc.html | 1
P22 | Remix a built-in unit | Phone | P22-Remix.dc.html | 1
P23 | Import by code | Phone | P23-Import.dc.html | 1
P24 | Checkout | Phone | P24-Checkout.dc.html | 3
P25 | Cancel subscription | Phone | P25-Cancel.dc.html | 1
P26 | Errors, offline & storage states | Phone | P26-States.dc.html | 4
P28 | Record letter sounds | Phone | P28-LetterSounds.dc.html | 1
P29 | Language settings | Phone | P29-Languages.dc.html | 2
P30 | Help & support | Phone | P30-Help.dc.html | 3
C06 | Placement quiz | Tablet | C06-Placement.dc.html | 1
C10 | Review lesson | Tablet | C10-Review.dc.html | 2
C25 | Exercise: trace | Tablet | C25-Trace.dc.html | 1
C26 | Exercise: clock setter | Tablet | C26-Clock.dc.html | 1
C27 | Exercise: build a word | Tablet | C27-BuildWord.dc.html | 1
C28 | Exercise: true or false | Tablet | C28-TrueFalse.dc.html | 1
C29 | First visit, offline & locked states | Tablet | C29-ChildStates.dc.html | 4
A02 | Teen sign-in | Tablet | A02-TeenSignIn.dc.html | 1
T00 | Teacher sign-up | Desktop | T00-TeacherSignUp.dc.html | 1
T05 | Teacher Badge Studio | Desktop | T05-TeacherBadges.dc.html | 3
S01 | School admin: licence & teachers | Desktop | S01-SchoolAdmin.dc.html | 2
S02 | School reports & library | Desktop | S02-SchoolReports.dc.html | 2
M01 | Moderation queue | Desktop | M01-Moderation.dc.html | 5

## Lists
Size | Points | Priority | Milestone | Title | Due | Status
XS | 1 | Must | MVP | Phase 1 — MVP (closed web beta) | 2027-02-26 | To do
S | 2 | Should | P2 | Phase 2 — Beta iteration + Classroom | 2027-04-23 | In progress
M | 3 | Could | P3 | Phase 3 — React Native Android app | 2027-07-30 | In review
L | 5 |  | P4 | Phase 4 — Breadth + public launch | 2027-11-05 | Done
XL | 8 |  | P5 | Phase 5 — Post-launch | 2028-06-30 | Blocked
Won't do